## Top Ten Risk List
ID | Risk and description | Classification | Probability | Level of impacts | Priority | Mitigation &Contingency Plans | Reasonability
1 | Task does not define clearly, lack of necessary work task, unreasonable allocation in each period | Schedule risk | Certain | Very High | 1 | 1) Use WBS to indentify task for project 2) Celebrate the meeting of senior to indentify task 3) Usually update plan
2 | The estimates are not exactly so schedule and plan to be changed | Schedule risk | Possible | Very High | 7 | 1) Use many technical to estimate. EX : Parametric, Wide band Delphi. 2) Training Team member using this technical. 3) Usually update plan.
3 | Constantly evolving technical updating, using modern equipment to development software -> increased budget | Budget risk | Likely | Moderate | 10 | 1) Negotiate with investor to add more finical 2) Update Budget Plan
4 | Investors do not support, investment in some functional expenses incurred unexpected | Budget risk | Imminent | High | 6 | 1) Meeting with inventor to discuss responsibility and accountability 2) Sign of contact with investor 3) Update project chapter
5 | Lack of budget to develop software. It may making Viking project failure because the key issues is not resolved | Budget risk | Certain | High | 3 | 1) Define scope of Viking project 2) Break scope into activities, tasks and sub-tasks 3) Conduct of Wideband Delphi to estimate time and cost for each task 4) Estimate cost of implementation for before the software is executed by adding sub-tasks
6 | Organization Structure is not established clearly. We may not good for communicate when the problem is happened | Quality risk | Imminent | High | 5 | 1) Update schedule and estimate resource for increased meeting for internal stakeholders. 2) Negotiate with stakeholders and get approval for changing schedule 3) Identify an moderator, key internal stakeholders for increased meeting 4) Implement discuss about for Responsibility, Accountability and Authority in increased meeting 5) Get approval (sign-off) for Responsibility, Accountability and Authority among stakeholders
7 | Not fully functional requirements, does not meet customer needs | Product Risk | Likely | Very High | 8 | 1) Do plan for other Phase Clearly. 2) Chosen staff have experience to communicate with stakeholder. 3) Training if we need. 4) Do change management Process to handing change request form stakeholder. 5) Validation & Verification with Stakeholder after that each phase.
8 | Customers do not know what they need, set out the requirement is ambiguous | Requirement risk | High | Very High | 2 | 1) Do plan for other Phase Clearly. 2) Chosen staff have experience to communicate with stakeholder. 3) Training if we need. 4) Do change management Process to handing change request form stakeholder. 5) Validation & Verification with Stakeholder about Requirement.
9 | Lack of experience in Change Management Process, we may not apply to using it. It can make project failure | Technical risk | Certain | High | 4 | 1) Update schedule and estimate needed elements for increased training Change Management Process training. 2) Negotiate with stakeholders and get approval for changing schedule 3) Identify an available expert in this division 4) Implement training for current staff
10 | Markets change, products are undesirable because of obsolescence or competition is too strong | Market risk | Possible | High | 9 | 1) Build clearly plan business strategy for product 2) Build team business 3) Ready to build plan if vision or world market change 4) Ready Sale Cost of Product, to contend market. 5) Project Sometime Get new requirement form New User to have solution, avoid product old in the market.