## Budget Estimation
ID | Task Name | Effort Estimate (% Confidence = 80%) | Budget Estimate | Assumption |  | Per hour
1 | Interview with customer | 3.28 days | 984 | 1 Requirement Engineer | Project manager | 40
2 | Software requirement specification | 6.28 days | 1884 | 9/12 uses case have been discovered, 1 Requirement Engineer | Requirement Engineer | 35
3 | Develop project plan | 7.8933 | 2763 | 1 Project Manager | Architect | 30
4 | Deploy infrastructure | 12.0667 | 3861 | Starts from the beginning, 2 persion | Developer | 25
5 | High level design | 7.5333 | 1808 | 9/12 uses case have been discovered, 1 Architect | Tester | 20
6 | Discover the rest of use cases | 6.64 | 1992 | 3 uses case, 1 Requiement Engineer | Others | 20
7 | Detail design modules in component 1 | 9.8933 | 4749 | Component 1 includes modules such as Member, Project, User, Lifecycles, Artifacts; 2 Architects
8 | Develop modules in component 1 | 20.2 | 20200 | Programming language is java, 5 Developers
9 | Test modules in component 1 | 9.56 | 3059 | Test environment available, 2 Tester
10 | Detail design modules in component 2 | 7.5333 | 3616 | Component 2 includes modules such as Roles, Permissions, Login, Issue; 2 Architects
11 | Develop modules in component 2 | 13.28 | 13280 | Programming language is java, 5 Developers
12 | Test modules in component 2 | 9.92 | 3174 | Test environment available, 2 Tester
13 | Detail design modules in component 3 | 17.1733 | 4122 | Component includes modules such as Communication, Report, Syschronize data, 1 Architect
14 | Develop modules in component 3 | 24.2533 | 14552 | Programming language is java, 3 Developers
15 | Test modules in component 3 | 10.2 | 3264 | Test environment unavailable, 2 Testers
16 | Develop User-guide | 4.2533 | 1021 | 1 Architect
17 | Training | 6.28 | 2010 | 2 person
18 | Perform acceptance testing | 19.2 | 6144 | Customer is friendly, 2 Testers
19 | Collect historical data | 5.28 | 845 | 1 person
|  |  | 93328 | TOTAL