## Summary Estimate
Name : |  | Role :
Date : | [9 empty] | (P+4ML+O)/6 | [6 empty] | (P-O)/6
ID | Task Name | Duong | Hien | Mung | Binh | Manh | Best | Most Likely | Pessimistic | Mean | 60% | 70% | 75% | 80% | 90% | 99% | Std Dev | Assumptions | Notes
1 | Inception | 13 | 18 | 13 | 17 | 17 | 12 | 16.5 | 20 | 16.3333 | 16.6667 | 17.0267 | 17.2267 | 17.4533 | 18.04 | 19.44
1.1 | Interview with customer | 3 | 2 | 2 | 4 | 3 | 2 | 3 | 4 | 3 | 3.0833 | 3.1733 | 3.2233 | 3.28 | 3.4267 | 3.7767 | 0.33333 | 1 Requirement Engineer
1.2 | Software requirement specification | 5 | 7 | 5 | 5 | 6 | 5 | 6 | 7 | 6 | 6.0833 | 6.1733 | 6.2233 | 6.28 | 6.4267 | 6.7767 | 0.33333 | 9/12 uses case have been discovered, 1 Requirement Engineer
1.3 | Develop project plan | 5 | 9 | 6 | 8 | 8 | 5 | 7.5 | 9 | 7.3333 | 7.5 | 7.68 | 7.78 | 7.8933 | 8.1867 | 8.8867 | 0.66667 | 1 Project Manager
2 | Elaboration | 26 | 23 | 28 | 21 | 25 | 15 | 24.5 | 31 | 24 | 24.6667 | 25.3867 | 25.7867 | 26.24 | 27.4133 | 30.2133
2.1 | Deploy infrastructure | 15 | 10 | 12 | 5 | 12 | 5 | 11 | 15 | 10.6667 | 11.0833 | 11.5333 | 11.7833 | 12.0667 | 12.8 | 14.55 | 1.6667 | Starts from the beginning | Discrepancy between Binh and Manh
2.2 | High level design | 4 | 7 | 9 | 9 | 7 | 4 | 7 | 9 | 6.8333 | 7.0417 | 7.2667 | 7.3917 | 7.5333 | 7.9 | 8.775 | 0.83333 | 9/12 uses case have been discovered, 1 Architect
2.4 | Discover the rest of use cases | 7 | 6 | 7 | 7 | 6 | 6 | 6.5 | 7 | 6.5 | 6.5417 | 6.5867 | 6.6117 | 6.64 | 6.7133 | 6.8883 | 0.16667 | 3 uses case, 1 Requiement Engineer
3 | Construction | 118 | 114 | 125 | 123 | 130 | 99 | 116.5 | 136 | 116.8333 | 118.375 | 120.04 | 120.965 | 122.0133 | 124.7267 | 131.2017
3.1 | Detail design modules in component 1 | 12 | 9 | 8 | 9 | 8 | 8 | 9 | 12 | 9.3333 | 9.5 | 9.68 | 9.78 | 9.8933 | 10.1867 | 10.8867 | 0.66667 | Component 1 includes modules such as Member, Project, User, Lifecycles, Artifacts; 2 Architects
3.2 | Develop modules in component 1 | 20 | 18 | 22 | 23 | 20 | 18 | 19 | 23 | 19.5 | 19.7083 | 19.9333 | 20.0583 | 20.2 | 20.5667 | 21.4417 | 0.83333 | Programming language is java, 5 Developers
3.3 | Test modules in component 1 | 7 | 8 | 9 | 10 | 11 | 7 | 9 | 11 | 9 | 9.1667 | 9.3467 | 9.4467 | 9.56 | 9.8533 | 10.5533 | 0.66667 | Test environment available, 2 Tester
3.4 | Detail design modules in component 2 | 15 | 10 | 13 | 12 | 12 | 4 | 7 | 9 | 6.8333 | 7.0417 | 7.2667 | 7.3917 | 7.5333 | 7.9 | 8.775 | 0.83333 | Component 2 includes modules such as Roles, Permissions, Login, Issue; 2 Architects
3.5 | Develop modules in component 2 | 12 | 13 | 14 | 13 | 14 | 12 | 13 | 14 | 13 | 13.0833 | 13.1733 | 13.2233 | 13.28 | 13.4267 | 13.7767 | 0.33333 | Programming language is java, 5 Developers
3.6 | Test modules in component 2 | 9 | 8 | 9 | 10 | 11 | 8 | 9.5 | 11 | 9.5 | 9.625 | 9.76 | 9.835 | 9.92 | 10.14 | 10.665 | 0.5 | Test environment available, 2 Tester
3.7 | Detail design modules in component 3 | 14 | 13 | 19 | 15 | 18 | 13 | 16.5 | 19 | 16.3333 | 16.5833 | 16.8533 | 17.0033 | 17.1733 | 17.6133 | 18.6633 | 1 | Component includes modules such as Communication, Report, Syschronize data, 1 Architect
3.8 | Develop modules in component 3 | 20 | 25 | 22 | 24 | 24 | 22 | 24 | 25 | 23.8333 | 23.9583 | 24.0933 | 24.1683 | 24.2533 | 24.4733 | 24.9983 | 0.5 | Programming language is java, 3 Developers
3.9 | Test modules in component 3 | 9 | 10 | 9 | 7 | 12 | 7 | 9.5 | 12 | 9.5 | 9.7083 | 9.9333 | 10.0583 | 10.2 | 10.5667 | 11.4417 | 0.83333 | Test environment unavailable, 2 Testers
4 | Transition | 27 | 28 | 29 | 23 | 29 | 22 | 29 | 32 | 28.3333 | 28.75 | 29.2 | 29.45 | 29.7333 | 30.4667 | 32.2167
4.1 | Develop User-guide | 5 | 3 | 2 | 2 | 3 | 2 | 4 | 5 | 3.8333 | 3.9583 | 4.0933 | 4.1683 | 4.2533 | 4.4733 | 4.9983 | 0.5 | 1 Architect
4.2 | Training | 7 | 5 | 7 | 6 | 7 | 5 | 6 | 7 | 6 | 6.0833 | 6.1733 | 6.2233 | 6.28 | 6.4267 | 6.7767 | 0.33333 | 2 person
4.3 | Perform acceptance testing | 15 | 20 | 20 | 15 | 19 | 15 | 19 | 20 | 18.5 | 18.7083 | 18.9333 | 19.0583 | 19.2 | 19.5667 | 20.4417 | 0.83333 | Customer is friendly, 2 Testers
5 | Close-out | 5 | 6 | 4 | 6 | 5 | 4 | 5 | 6 | 5 | 5.0833 | 5.1733 | 5.2233 | 5.28 | 5.4267 | 5.7767
5.1 | Collect historical data | 5 | 6 | 4 | 6 | 5 | 4 | 5 | 6 | 5 | 5.0833 | 5.1733 | 5.2233 | 5.28 | 5.4267 | 5.7767 | 0.33333 | 1 person
Total | [6 empty] | 152 | 191.5 | 225 | 190.5 | 193.5417 | 196.8267 | 198.6517 | 200.72 | 206.0733 | 218.8483 | Totals

## Percentage Confidence
% Confidence | Calculation
2% | Expected Case - (2 *Standard Deviation)
10% | Expected Case - (1.28 * Standard Deviation)
16% | Expected Case - (1 * Standard Deviation)
20% | Expected Case - (.84 * Standard Deviation)
25% | Expected Case - (.67 * Standard Deviation)
30% | Expected Case - (.52 * Standard Deviation)
40% | Expected Case - (.25 * Standard Deviation)
50% | Expected Case
60% | Expected Case + (.25 *Standard Deviation)
70% | Expected Case + (.52 * Standard Deviation)
75% | Expected Case + (.67 * Standard Deviation)
80% | Expected Case + (.84 * Standard Deviation)
84% | Expected Case + (1 * Standard Deviation)
90% | Expected Case + (1.28 * Standard Deviation)
98% | Expected Case + (2 * Standard Deviation)
% of Outcomes | Complex SD Divisor
10% | 0.25
20% | 0.51
30% | 0.77
40% | 1
50% | 1.4
60% | 1.7
70% | 2.1
80% | 2.6
90% | 3.3
99.7% | 6