## Sheet1
Hien Nguyen |  |  |  | Date: |  |  | Units:
Goal Statement:
Task Name | Est 1 | ∆1 | ∆2 | ∆3 | ∆4 | Total | Assumptions
Interview with customer | 1 | 1 |  |  |  | 2 | 1 Requirement Engineer
Software requirement specification | 8 | -1 |  |  |  | 7 | 9/12 uses case have been discovered, 1 Requirement Engineer
Develop project plan | 11 | -1 | -1 |  |  | 9 | 1 Project Manager
Deploy infrastructure | 9 | 1 |  |  |  | 10 | Starts from the beginning
High level design | 5 | 2 |  |  |  | 7 | 9/12 uses case have been discovered, 1 Architect
Discover the rest of use cases | 5 | 1 |  |  |  | 6 | 3 uses case, 1 Requiement Engineer
Detail design modules in component 1 | 10 | -1 |  |  |  | 9 | Component 1 includes modules such as Member, Project, User, Lifecycles, Artifacts; 2 Architects
Develop modules in component 1 | 20 | -2 |  |  |  | 18 | Programming language is java, 5 Developers
Test modules in component 1 | 8 |  |  |  |  | 8 | Test environment available, 2 Tester
Detail design modules in component 2 | 9 | -1 | 2 |  |  | 10 | Component 2 includes modules such as Roles, Permissions, Login, Issue; 2 Architects
Develop modules in component 2 | 13 | 1 | -1 |  |  | 13 | Programming language is java, 5 Developers
Test modules in component 2 | 9 | -1 |  |  |  | 8 | Test environment available, 2 Tester
Detail design modules in component 3 | 12 | 1 |  |  |  | 13 | Component includes modules such as Communication, Report, Syschronize data, 1 Architect
Develop modules in component 3 | 26 | -2 | 1 |  |  | 25 | Programming language is java, 3 Developers
Test modules in component 3 | 9 | 1 |  |  |  | 10 | Test environment unavailable, 2 Testers
Develop User-guide | 4 | -1 |  |  |  | 3 | 1 Architect
Training | 5 |  |  |  |  | 5 | 2 person
Perform acceptance testing | 19 | 1 |  |  |  | 20 | Customer is friendly, 2 Testers
Close-out | 8 | -2 |  |  |  | 6 | 1 person
Delta Total |  | -3 | 1 | 0 | 0
Total Estimate | 191 | 188 | 189 | 189 | 189 | 189
THANK YOU FOR YOUR BUSINESS!