## List Tasks
ID | Task Name
1 | Interview with customer
2 | Software requirement specification
3 | Develop project plan
4 | Deploy infrastructure
5 | High level design
6 | Discover the rest of use cases
7 | Detail design modules in component 1
8 | Develop modules in component 1
9 | Test modules in component 1
10 | Detail design modules in component 2
11 | Develop modules in component 2
12 | Test modules in component 2
13 | Detail design modules in component 3
14 | Develop modules in component 3
15 | Test modules in component 3
16 | Develop User-guide
17 | Training
18 | Perform acceptance testing
19 | Collect historical data

## List Assumption
ID | Assumptions
1 | 75% (9/12) uses case have been discovered
2 | Starts from the beginning
3 | Component 1 includes modules such as Member, Project, User, Lifecycles, Artifacts
4 | Programming language is java
5 | Test environment available
6 | Component 2 includes modules such as Roles, Permissions, Login, Issue
7 | Programming language is java
8 | Test environment available
9 | Component 3 includes modules such as Communication, Report, Syschronize data
10 | Programming language is java
11 | Test environment unavailable
12 | Customer is friendly
12 | Project includes: 1 Project Manager, 1 Requirement Engineer, 6 Developer, 2 Tester