## Planned
Planned Weekly Effort W#1 | [9 empty] | Planned Weekly Effort W#1 | [9 empty] | Planned Weekly Effort W#1 | [9 empty] | Planned Weekly Effort W#1
Name: | Duong Nguyen | Starting Date: |  | 2010-09-13 | [5 empty] | Name: | Hien Nguyen | Starting Date: |  | 2010-09-13 | [5 empty] | Name: | Binh Huynh | Starting Date: |  | 2010-09-13 | [5 empty] | Name: | Mung Nguyen | Starting Date: |  | 2010-09-13
Course: | SMA | 2010-09-13 | 2010-09-14 | 2010-09-15 | 2010-09-16 | 2010-09-17 | 2010-09-18 | 2010-09-19 | Total | Course | SMA | 2010-09-13 | 2010-09-14 | 2010-09-15 | 2010-09-16 | 2010-09-17 | 2010-09-18 | 2010-09-19 | Total | Course: | SMA | 2010-09-13 | 2010-09-14 | 2010-09-15 | 2010-09-16 | 2010-09-17 | 2010-09-18 | 2010-09-19 | Total | Course | SMA | 2010-09-13 | 2010-09-14 | 2010-09-15 | 2010-09-16 | 2010-09-17 | 2010-09-18 | 2010-09-19 | Total
| Task | 2010-09-13 | 2010-09-14 | 2010-09-15 | 2010-09-16 | 2010-09-17 | 2010-09-18 | 2010-09-19 |  |  | Task | 2010-09-13 | 2010-09-14 | 2010-09-15 | 2010-09-16 | 2010-09-17 | 2010-09-18 | 2010-09-19 |  |  | Task | 2010-09-13 | 2010-09-14 | 2010-09-15 | 2010-09-16 | 2010-09-17 | 2010-09-18 | 2010-09-19 |  |  | Task | 2010-09-13 | 2010-09-14 | 2010-09-15 | 2010-09-16 | 2010-09-17 | 2010-09-18 | 2010-09-19
| In Class | 2010-09-13: 2.5; 2010-09-15: 2.5; 2010-09-16: 0; 2010-09-17: 2.5 | 7.5 |  | In Class | 2.5 |  | 2.5 |  | 2.5 |  |  | 7.5 |  | In Class | 2.3 |  | 2.3 |  | 2.3 |  |  | 6.9 |  | In Class | 2.5 |  | 2.5 |  | 2.5 |  |  | 7.5
| Team Meetings | 2010-09-14: 0.5; 2010-09-18: 1 | 1.5 |  | Team Meetings |  | 1 |  |  |  | 1 |  | 2 |  | Team Meetings |  | 1.3 |  | 1.3 |  | 1.3 |  | 3.9 |  | Team Meetings |  | 1 | [5 empty] | 1
| Reading | [7 empty] | 1 |  | Reading |  | 1 | 1 | 1 | 2 |  | 1 | 6 |  | Reading |  | 1.3 |  | 1.3 |  |  |  | 2.6 |  | Reading |  | 1 |  | 1.5 |  |  |  | 2.5 | bar: 2010-09-19
| Homework | [7 empty] | 3 |  | Homework | [6 empty] | 2 | 2 |  | Homework | [7 empty] | 0 |  | Homework | [7 empty] | 0 | bar: 2010-09-17 to 2010-09-19
| Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0
| Team Assignment | 2010-09-16: 1; 2010-09-17: 1; 2010-09-18: 1; 2010-09-19: 1.5 | 4.5 |  | Team Assignment | [7 empty] | 0 |  | Team Assignment | [7 empty] | 0 |  | Team assignment |  |  | 1 |  | 1 | 2 |  | 4
| Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0
| Total | 2.5 | 0.5 | 2.5 | 1 | 4.5 | 3 | 3.5 | 17.5 |  | Total | 2.5 | 2 | 3.5 | 1 | 4.5 | 1 | 3 | 17.5 |  | Total | 2.3 | 2.6 | 2.3 | 2.6 | 2.3 | 1.3 | 0 | 13.4 |  | Total | 2.5 | 2 | 3.5 | 1.5 | 3.5 | 2 | 0 | 15
Planned Weekly Effort W#2 | [9 empty] | Planned Weekly Effort W#2 | [9 empty] | Planned Weekly Effort W#2 | [9 empty] | Weekly Effort Effort W#2
Name: | Duong nguyen | 2010-09-13: Starting Date:; 2010-09-15: 2010-09-20 |  | Name: | Hien Nguyen | Starting Date: |  | 2010-09-20 | [5 empty] | Name: | Binh Huynh | Starting Date: |  | 2010-09-20 | [5 empty] | Name: | Mung Nguyen | Starting Date: |  | 2010-09-20
Course: | SMA | 2010-09-20 | 2010-09-21 | 2010-09-22 | 2010-09-23 | 2010-09-24 | 2010-09-25 | 2010-09-26 | Total | Course | SMA | 2010-09-20 | 2010-09-21 | 2010-09-22 | 2010-09-23 | 2010-09-24 | 2010-09-25 | 2010-09-26 | Total | Course: | SMA | 2010-09-20 | 2010-09-21 | 2010-09-22 | 2010-09-23 | 2010-09-24 | 2010-09-25 | 2010-09-26 | Total | Course | SMA | 2010-09-20 | 2010-09-21 | 2010-09-22 | 2010-09-23 | 2010-09-24 | 2010-09-25 | 2010-09-26 | Total
| Task | 2010-09-20 | 2010-09-21 | 2010-09-22 | 2010-09-23 | 2010-09-24 | 2010-09-25 | 2010-09-26 |  |  | Task | 2010-09-20 | 2010-09-21 | 2010-09-22 | 2010-09-23 | 2010-09-24 | 2010-09-25 | 2010-09-26 |  |  | Task | 2010-09-20 | 2010-09-21 | 2010-09-22 | 2010-09-23 | 2010-09-24 | 2010-09-25 | 2010-09-26 |  |  | Task | 2010-09-20 | 2010-09-21 | 2010-09-22 | 2010-09-23 | 2010-09-24 | 2010-09-25 | 2010-09-26
| In Class | 2010-09-20: 2.5; 2010-09-22: 2.5; 2010-09-24: 2.5 | 7.5 |  | In Class | 2.5 |  | 2.5 |  | 2.5 |  |  | 7.5 |  | In Class | 2.3 |  | 2.3 |  | 2.3 |  |  | 6.9 |  | In Class | 2.5 |  | 2.5 |  | 2.5 |  |  | 7.5
| Team Meetings | [7 empty] | 4 |  | Team Meetings | 1 | 1 |  | 2 |  | 1 |  | 5 |  | Team Meetings |  | 1.3 |  | 1.3 |  | 1.3 |  | 3.9 |  | Team Meetings |  | 2 |  | 1 |  | 1 |  | 4 | bar: 2010-09-20 to 2010-09-21; 2010-09-23; 2010-09-25
| Reading | [7 empty] | 2 |  | Reading |  | 1 | 1 | 1 | 2 |  | 3 | 8 |  | Reading | 1 |  |  | 1 |  |  | 1 | 3 |  | Reading |  | 1 | 1 | 1.5 |  | 1 |  | 4.5 | bar: 2010-09-20; 2010-09-24
| Homework | 2010-09-21: 1; 2010-09-25: 2; 2010-09-26: 2 | 5 |  | Homework | 1 | [5 empty] | 2 | 3 |  | Homework |  |  | 2 |  |  |  |  | 2 |  | Homework |  |  | 1 | 2 |  |  |  | 3
| Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0
| Team Assignment | [7 empty] | 5 |  | Team Assignment | [7 empty] | 0 |  | Team Assignment | [7 empty] | 0 |  | Team assignment |  |  |  |  | 1 | 3 |  | 4 | bar: 2010-09-21; 2010-09-23 to 2010-09-26
| Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0 |  | Others… |  |  |  | 1 |  |  |  | 1 |  | Meetings with Faculty
| Total | 4.5 | 3 | 2.5 | 2 | 4.5 | 4 | 3 | 23.5 |  | Total | 4.5 | 2 | 3.5 | 3 | 4.5 | 1 | 5 | 23.5 |  | Total | 3.3 | 1.3 | 4.3 | 3.3 | 2.3 | 1.3 | 1 | 16.8 |  | Total | 2.5 | 3 | 4.5 | 4.5 | 3.5 | 5 | 0 | 23
Planned Weekly Effort W#3 | [9 empty] | Planned Weekly Effort W#3 | [9 empty] | Planned Weekly Effort W#3 | [9 empty] | Weekly Effort Effort W#3
Name: | Duong nguyen | 2010-09-20: Starting Date:; 2010-09-22: 2010-09-27 |  | Name: | Hien Nguyen | Starting Date: |  | 2010-09-27 | [5 empty] | Name: | Binh Huynh | Starting Date: |  | 2010-09-27 | [5 empty] | Name: | Mung Nguyen | Starting Date: |  | 2010-09-27
Course: | SMA | 2010-09-27 | 2010-09-28 | 2010-09-29 | 2010-09-30 | 2010-10-01 | 2010-10-02 | 2010-10-03 | Total | Course | SMA | 2010-09-27 | 2010-09-28 | 2010-09-29 | 2010-09-30 | 2010-10-01 | 2010-10-02 | 2010-10-03 | Total | Course: | SMA | 2010-09-27 | 2010-09-28 | 2010-09-29 | 2010-09-30 | 2010-10-01 | 2010-10-02 | 2010-10-03 | Total | Course | SMA | 2010-09-27 | 2010-09-28 | 2010-09-29 | 2010-09-30 | 2010-10-01 | 2010-10-02 | 2010-10-03 | Total
| Task | 2010-09-27 | 2010-09-28 | 2010-09-29 | 2010-09-30 | 2010-10-01 | 2010-10-02 | 2010-10-03 |  |  | Task | 2010-09-27 | 2010-09-28 | 2010-09-29 | 2010-09-30 | 2010-10-01 | 2010-10-02 | 2010-10-03 |  |  | Task | 2010-09-27 | 2010-09-28 | 2010-09-29 | 2010-09-30 | 2010-10-01 | 2010-10-02 | 2010-10-03 |  |  | Task | 2010-09-27 | 2010-09-28 | 2010-09-29 | 2010-09-30 | 2010-10-01 | 2010-10-02 | 2010-10-03
| In Class | 2010-09-27: 2.5; 2010-09-29: 2.5; 2010-10-01: 2.5 | 7.5 |  | In Class | 2.5 |  | 2.5 |  | 2.5 |  |  | 7.5 |  | In Class | 2.3 |  | 2.3 |  | 2.3 |  |  | 6.9 |  | In Class | 2.5 |  | 2.5 |  | 2.5 |  |  | 7.5
| Team Meetings | [7 empty] | 3 |  | Team Meetings | 1 | 1 |  | 2 |  | 1 |  | 5 |  | Team Meetings |  | 1.3 |  | 1.3 |  | 1.3 |  | 3.9 |  | Team Meetings | 1 | 1 |  | 1 |  | 0.5 |  | 3.5 | bar: 2010-09-27 to 2010-09-28; 2010-10-02
| Reading | [7 empty] | 2 |  | Reading |  | 1 | 1 | 1 | 2 |  | 3 | 8 |  | Reading | 1 | 1 |  | 1 |  | 1 | 1 | 5 |  | Reading |  | 2 | 1 |  | 1 |  |  | 4 | bar: 2010-09-29; 2010-10-01
| Homework | [7 empty] | 2 |  | Homework |  |  |  |  | 1 |  | 2 | 3 |  | Homework |  |  | 2 |  |  |  |  | 2 |  | Homework | [7 empty] | 0 | bar: 2010-10-02 to 2010-10-03
| Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0
| Team Assignment | [7 empty] | 3 |  | Team Assignment | 1 |  | 1 |  | 1 |  |  | 3 |  | Team Assignment | 1 |  | 2 |  | 1 |  |  | 4 |  | Team assignment | 1 |  |  | 1 | 3 |  |  | 5 | bar: 2010-09-28; 2010-10-02 to 2010-10-03
| Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0 |  | Others… | [7 empty] | 0 |  | Meetings with Faculty
| Total | 3.5 | 2 | 3.5 | 0 | 3.5 | 3 | 2 | 17.5 |  | Total | 4.5 | 2 | 4.5 | 3 | 6.5 | 1 | 5 | 26.5 |  | Total | 4.3 | 2.3 | 6.3 | 2.3 | 3.3 | 2.3 | 1 | 21.8 |  | Total | 4.5 | 3 | 3.5 | 2 | 6.5 | 0.5 | 0 | 20
Planned Weekly Effort W#4 | [9 empty] | Planned Weekly Effort W#4 | [9 empty] | Planned Weekly Effort W#4 | [9 empty] | Planned Weekly Effort W#4
Name: | Duong nguyen | 2010-09-27: Starting Date:; 2010-09-29: 2010-10-04 |  | Name: | Hien Nguyen | Starting Date: |  | 2010-10-04 | [5 empty] | Name: | Binh Huynh | Starting Date: |  | 2010-10-04 | [5 empty] | Name: | Mung Nguyen | Starting Date: |  | 2010-10-04
Course: | SMA | 2010-10-04 | 2010-10-05 | 2010-10-06 | 2010-10-07 | 2010-10-08 | 2010-10-09 | 2010-10-10 | Total | Course | SMA | 2010-10-04 | 2010-10-05 | 2010-10-06 | 2010-10-07 | 2010-10-08 | 2010-10-09 | 2010-10-10 | Total | Course: | SMA | 2010-10-04 | 2010-10-05 | 2010-10-06 | 2010-10-07 | 2010-10-08 | 2010-10-09 | 2010-10-10 | Total | Course: | SMA | 2010-10-04 | 2010-10-05 | 2010-10-06 | 2010-10-07 | 2010-10-08 | 2010-10-09 | 2010-10-10 | Total
| Task | 2010-10-04 | 2010-10-05 | 2010-10-06 | 2010-10-07 | 2010-10-08 | 2010-10-09 | 2010-10-10 |  |  | Task | 2010-10-04 | 2010-10-05 | 2010-10-06 | 2010-10-07 | 2010-10-08 | 2010-10-09 | 2010-10-10 |  |  | Task | 2010-10-04 | 2010-10-05 | 2010-10-06 | 2010-10-07 | 2010-10-08 | 2010-10-09 | 2010-10-10 |  |  | Task | 2010-10-04 | 2010-10-05 | 2010-10-06 | 2010-10-07 | 2010-10-08 | 2010-10-09 | 2010-10-10
| In Class | 2010-10-04: 2.5; 2010-10-06: 2.5; 2010-10-08: 2.5 | 7.5 |  | In Class | 2.5 |  | 2.5 |  | 2.5 |  |  | 7.5 |  | In Class | 2.5 |  | 2.5 |  | 2.5 |  |  | 7.5 |  | In Class | 2.5 |  | 2.5 |  | 2.5 |  |  | 7.5
| Team Meetings | 2010-10-04: 1; 2010-10-05: 1.5; 2010-10-07: 1.5; 2010-10-09: 1 | 5 |  | Team Meetings | 1 | 1 |  | 1 |  | 1 |  | 4 |  | Team Meetings | 1 | 1.5 |  | 1.5 |  | 1 |  | 5 |  | Team Meetings | 1 | 1.5 |  | 1.5 |  | 1 |  | 5
| Reading | [7 empty] | 1 |  | Reading |  | 1 | 1 | 1 | 2 |  | 3 | 8 |  | Reading |  |  | 1 | 2 |  |  | 1 | 4 |  | Reading |  |  |  | 2 |  |  | 1 | 3 | bar: 2010-10-10
| Homework | 2010-10-09: 2 | 2 |  | Homework |  |  |  |  | 1 |  | 2 | 3 |  | Homework |  |  |  |  | 1 |  |  | 1 |  | Homework | [5 empty] | 2 | 1 | 3
| Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0
| Team Assignment | 2010-10-05: 0.5; 2010-10-06: 1.5; 2010-10-07: 0.5; 2010-10-10: 2 | 4.5 |  | Team Assignment | 2 |  | 1 |  | 2 |  |  | 5 |  | Team Assignment |  | 2 |  | 1 |  |  |  | 3 |  | Team Assignment |  | 2 |  | 0.5 |  |  |  | 2.5
| Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0
| Total | 3.5 | 2 | 4 | 2 | 2.5 | 3 | 3 | 20 |  | Total | 5.5 | 2 | 4.5 | 2 | 7.5 | 1 | 5 | 27.5 |  | Total | 3.5 | 3.5 | 3.5 | 4.5 | 3.5 | 1 | 1 | 20.5 |  | Total | 3.5 | 3.5 | 2.5 | 4 | 2.5 | 3 | 2 | 21
Planned Weekly Effort W#5 | [9 empty] | Planned Weekly Effort W#5 | [9 empty] | Planned Weekly Effort W#5 | [9 empty] | Planned Weekly Effort W#5
Name: | Duong nguyen | 2010-10-04: Starting Date:; 2010-10-06: 2010-10-11 |  | Name: | Hien Nguyen | Starting Date: |  | 2010-10-11 | [5 empty] | Name: | Binh Huynh | Starting Date: |  | 2010-10-11 | [5 empty] | Name: | Mung Nguyen | Starting Date: |  | 2010-10-11
Course: | SMA | 2010-10-11 | 2010-10-12 | 2010-10-13 | 2010-10-14 | 2010-10-15 | 2010-10-16 | 2010-10-17 | Total | Course | SMA | 2010-10-11 | 2010-10-12 | 2010-10-13 | 2010-10-14 | 2010-10-15 | 2010-10-16 | 2010-10-17 | Total | Course | SMA | 2010-10-11 | 2010-10-12 | 2010-10-13 | 2010-10-14 | 2010-10-15 | 2010-10-16 | 2010-10-17 | Total | Course | SMA | 2010-10-11 | 2010-10-12 | 2010-10-13 | 2010-10-14 | 2010-10-15 | 2010-10-16 | 2010-10-17 | Total
| Task | 2010-10-11 | 2010-10-12 | 2010-10-13 | 2010-10-14 | 2010-10-15 | 2010-10-16 | 2010-10-17 |  |  | Task | 2010-10-11 | 2010-10-12 | 2010-10-13 | 2010-10-14 | 2010-10-15 | 2010-10-16 | 2010-10-17 |  |  | Task | 2010-10-11 | 2010-10-12 | 2010-10-13 | 2010-10-14 | 2010-10-15 | 2010-10-16 | 2010-10-17 |  |  | Task | 2010-10-11 | 2010-10-12 | 2010-10-13 | 2010-10-14 | 2010-10-15 | 2010-10-16 | 2010-10-17
| In Class | 2010-10-11: 2.5; 2010-10-13: 2.5; 2010-10-15: 2.5 | 7.5 |  | In Class | 2.5 |  | 2.5 |  | 2.5 |  |  | 7.5 |  | In Class | 2.5 |  | 2.5 |  | 2.5 |  |  | 7.5 |  | In Class | 2.5 |  | 2.5 |  | 2.5 |  |  | 7.5
| Team Meetings | 2010-10-12: 1.5; 2010-10-14: 1.5; 2010-10-16: 1 | 4 |  | Team Meetings |  | 1 |  | 1 |  | 1 |  | 3 |  | Team Meetings | 1 | 1 |  | 1 |  | 1 |  | 4 |  | Team Meetings |  | 1 |  | 1 |  | 1 |  | 3
| Reading | 2010-10-15: 2 | 2 |  | Reading |  | 1 |  | 1 |  |  | 2 | 4 |  | Reading |  | 1 |  | 1 |  | 1 |  | 3 |  | Reading |  | 1 |  | 1 |  |  | 2 | 4
| Homework | 2010-10-16: 2; 2010-10-17: 0.5 | 2.5 |  | Homework |  |  |  |  | 1 |  | 2 | 3 |  | Homework | [6 empty] | 2 | 2 |  | Homework | [5 empty] | 1 | 1 | 2
| Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0 |  | Labs | [6 empty] | 2 | 2 |  | Labs | [7 empty] | 0
| Team Assignment | 1 | 0.5 |  | 0.5 | 1 |  | 1 | 4 |  | Team Assignment | 2 |  | 0.5 |  |  |  |  | 2.5 |  | Team Assignment | 2 |  | 1 | 1 | 1 |  |  | 5 |  | Team Assignment | 1 | [6 empty] | 1
| Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0
| Total | 3.5 | 2 | 2.5 | 2 | 5.5 | 3 | 1.5 | 20 |  | Total | 4.5 | 2 | 3 | 2 | 3.5 | 1 | 4 | 20 |  | Total | 5.5 | 2 | 3.5 | 3 | 3.5 | 2 | 4 | 23.5 |  | Total | 3.5 | 2 | 2.5 | 2 | 2.5 | 2 | 3 | 17.5

## Actual-Week 1
Weekly Effort Recording Form-W#1 | [9 empty] | Weekly Effort Recording Form W#1 | [9 empty] | Weekly Effort Recording Form W#1 | [9 empty] | Weekly Effort Recording Form W#1
Name: | Duong Nguyen | Starting Date: |  | 2010-09-13 | [5 empty] | Name: | Hien Nguyen | Starting Date: |  | 2010-09-13 | [5 empty] | Name: | Binh Huynh | Starting Date: |  | 2010-09-13 | [5 empty] | Name: | Mung Nguyen | Starting Date: |  | 2010-09-13
Course: | ADP | 2010-09-13 | 2010-09-14 | 2010-09-15 | 2010-09-16 | 2010-09-17 | 2010-09-18 | 2010-09-19 | Total | Course | SMA | 2010-09-13 | 2010-09-14 | 2010-09-15 | 2010-09-16 | 2010-09-17 | 2010-09-18 | 2010-09-19 | Total | Course: | ADP | 2010-09-13 | 2010-09-14 | 2010-09-15 | 2010-09-16 | 2010-09-17 | 2010-09-18 | 2010-09-19 | Total | Course: | ADP | 2010-09-13 | 2010-09-14 | 2010-09-15 | 2010-09-16 | 2010-09-17 | 2010-09-18 | 2010-09-19 | Total
| Task | 2010-09-13 | 2010-09-14 | 2010-09-15 | 2010-09-16 | 2010-09-17 | 2010-09-18 | 2010-09-19 |  |  | Task | 2010-09-13 | 2010-09-14 | 2010-09-15 | 2010-09-16 | 2010-09-17 | 2010-09-18 | 2010-09-19 |  |  | Task | 2010-09-13 | 2010-09-14 | 2010-09-15 | 2010-09-16 | 2010-09-17 | 2010-09-18 | 2010-09-19 |  |  | Task | 2010-09-13 | 2010-09-14 | 2010-09-15 | 2010-09-16 | 2010-09-17 | 2010-09-18 | 2010-09-19
| In Class | 2010-09-13: 2; 2010-09-15: 2; 2010-09-17: 2 | 6 |  | In Class | 2.5 |  | 2.5 |  | 2.5 |  |  | 7.5 |  | In Class | 2.3 |  | 2.3 |  | 2.3 |  |  | 6.9 |  | In Class | 2.5 |  | 2.5 |  | 2.5 |  |  | 7.5
| Team Meetings | [7 empty] | 2 |  | Team Meetings |  | 1 |  |  |  | 1 |  | 2 |  | Team Meetings |  | 1 |  |  |  | 1 |  | 2 |  | Team Meetings |  | 1 |  |  |  | 1 |  | 2 | bar: 2010-09-14; 2010-09-18
| Reading | [7 empty] | 0 |  | Reading |  | 0.5 | 1 | 0.5 | 2 |  | 2 | 6 |  | Reading |  |  |  | 1.3 |  |  |  | 1.3 |  | Reading |  | 1 |  | 1.5 |  |  |  | 2.5
| Homework | 2010-09-19: 4 | 4 |  | Homework | [6 empty] | 2 | 2 |  | Homework | [7 empty] | 0 |  | Homework | [7 empty] | 0
| Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0
| Team Assignment | 2010-09-16: 0.5; 2010-09-17: 1.5 | 0 |  | Team Assignment | [7 empty] | 0 |  | Team Assignment | [7 empty] | 0 |  | Team Assignment |  |  |  |  | 1 | 3 |  | 4
| Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0
| Total | 2 | 1 | 2 | 0.5 | 3.5 | 1 | 4 | 12 |  | Total | 2.5 | 1.5 | 3.5 | 0.5 | 4.5 | 1 | 4 | 17.5 |  | Total | 2.3 | 1 | 2.3 | 1.3 | 2.3 | 1 | 0 | 10.2 |  | Total | 2.5 | 2 | 2.5 | 1.5 | 3.5 | 4 | 0 | 16

## Actual-Week 2
Weekly Effort Recording Form W#2 | [9 empty] | Weekly Effort Recording Form W#2 | [9 empty] | Weekly Effort Recording Form W#2 | [9 empty] | Weekly Effort Recording Form W#2
Name: | Duong Nguyen | Starting Date: |  | 2010-09-20 | [5 empty] | Name: | Hien Nguyen | Starting Date: |  | 2010-09-20 | [5 empty] | Name: | Binh Huynh | Starting Date: |  | 2010-09-20 | [5 empty] | Name: | Mung Nguyen | Starting Date: |  | 2010-09-20
Course: | SMA | 2010-09-20 | 2010-09-21 | 2010-09-22 | 2010-09-23 | 2010-09-24 | 2010-09-25 | 2010-09-26 | Total | Course | SMA | 2010-09-20 | 2010-09-21 | 2010-09-22 | 2010-09-23 | 2010-09-24 | 2010-09-25 | 2010-09-26 | Total | Course | SMA | 2010-09-20 | 2010-09-21 | 2010-09-22 | 2010-09-23 | 2010-09-24 | 2010-09-25 | 2010-09-26 | Total | Course: | SMA | 2010-09-20 | 2010-09-21 | 2010-09-22 | 2010-09-23 | 2010-09-24 | 2010-09-25 | 2010-09-26 | Total
| Task | 2010-09-20 | 2010-09-21 | 2010-09-22 | 2010-09-23 | 2010-09-24 | 2010-09-25 | 2010-09-26 |  |  | Task | 2010-09-20 | 2010-09-21 | 2010-09-22 | 2010-09-23 | 2010-09-24 | 2010-09-25 | 2010-09-26 |  |  | Task | 2010-09-20 | 2010-09-21 | 2010-09-22 | 2010-09-23 | 2010-09-24 | 2010-09-25 | 2010-09-26 |  |  | Task | 2010-09-20 | 2010-09-21 | 2010-09-22 | 2010-09-23 | 2010-09-24 | 2010-09-25 | 2010-09-26
| In Class | 2010-09-20: 2.5; 2010-09-22: 2.5; 2010-09-24: 2.5 | 7.5 |  | In Class | 2.5 |  | 2.5 |  | 2.5 |  |  | 7.5 |  | In Class |  |  | 2.5 |  | 2.5 |  |  | 5 |  | In Class | 2.5 |  | 2.5 |  | 2.5 |  |  | 7.5
| Team Meetings | 2010-09-20: 1.5; 2010-09-21: 1.5; 2010-09-23: 3; 2010-09-25: 1 | 7 |  | Team Meetings | 1.5 | 1.5 |  | 3 |  |  |  | 6 |  | Team Meetings |  | 1.5 |  | 1 |  |  |  | 2.5 |  | Team Meetings |  | 1.5 |  | 3 |  | 1 |  | 5.5
| Reading | [7 empty] | 2 |  | Reading |  | 0.5 | 0.5 | 1 |  |  |  | 2 |  | Reading | 1 | 1 | 1.3 | 2 | 1.3 |  |  | 6.6 |  | Reading | 2 | [6 empty] | 2 | bar: 2010-09-20; 2010-09-25
| Homework | 2010-09-21: 1.5; 2010-09-25: 2.5; 2010-09-26: 2 | 6 |  | Homework | 0.5 |  |  | 1 |  |  |  | 1.5 |  | Homework |  | 1 |  | 3 |  |  |  | 4 |  | Homework |  |  | 1 | 1 |  |  |  | 2
| Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0
| Team Assignment | 2010-09-21: 1.5; 2010-09-23: 0.5; 2010-09-24: 3 | 5 |  | Team Assignment | [7 empty] | 0 |  | Team Assignment | 1 |  |  |  | 3 |  |  | 4 |  | Team Assignment | 2 | [6 empty] | 2
| Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0
| Total | 5 | 4.5 | 2.5 | 3.5 | 5.5 | 4.5 | 2 | 27.5 |  | Total | 4.5 | 2 | 3 | 5 | 2.5 | 0 | 0 | 17 |  | Total | 2 | 3.5 | 3.8 | 6 | 6.8 | 0 | 0 | 22.1 |  | Total | 6.5 | 1.5 | 3.5 | 4 | 2.5 | 1 | 0 | 19

## Actual-Week 3
Weekly Effort Recording Form W#3 | [9 empty] | Weekly Effort Recording Form W#3 | [9 empty] | Weekly Effort Recording Form W#3 | [9 empty] | Weekly Effort Recording Form W#3 | [9 empty] | Weekly Effort Recording Form W#3
Name: | Duong Nguyen | Starting Date: |  | 2010-09-27 | [5 empty] | Name: | Hien Nguyen | Starting Date: |  | 2010-09-27 | [5 empty] | Name: | Binh Huynh | Starting Date: |  | 2010-09-27 | [5 empty] | Name: | Mung Nguyen | Starting Date: |  | 2010-09-27 | [5 empty] | Name: | Manh Nguyen | Starting Date: |  | 2010-09-27
Course: | SMA | 2010-09-27 | 2010-09-28 | 2010-09-29 | 2010-09-30 | 2010-10-01 | 2010-10-02 | 2010-10-03 | Total | Course | SMA | 2010-09-27 | 2010-09-28 | 2010-09-29 | 2010-09-30 | 2010-10-01 | 2010-10-02 | 2010-10-03 | Total | Course | SMA | 2010-09-27 | 2010-09-28 | 2010-09-29 | 2010-09-30 | 2010-10-01 | 2010-10-02 | 2010-10-03 | Total | Course: | SMA | 2010-09-27 | 2010-09-28 | 2010-09-29 | 2010-09-30 | 2010-10-01 | 2010-10-02 | 2010-10-03 | Total | Course: | SMA | 2010-09-27 | 2010-09-28 | 2010-09-29 | 2010-09-30 | 2010-10-01 | 2010-10-02 | 2010-10-03 | Total
| Task | 2010-09-27 | 2010-09-28 | 2010-09-29 | 2010-09-30 | 2010-10-01 | 2010-10-02 | 2010-10-03 |  |  | Task | 2010-09-27 | 2010-09-28 | 2010-09-29 | 2010-09-30 | 2010-10-01 | 2010-10-02 | 2010-10-03 |  |  | Task | 2010-09-27 | 2010-09-28 | 2010-09-29 | 2010-09-30 | 2010-10-01 | 2010-10-02 | 2010-10-03 |  |  | Task | 2010-09-27 | 2010-09-28 | 2010-09-29 | 2010-09-30 | 2010-10-01 | 2010-10-02 | 2010-10-03 |  |  | Task | 2010-09-27 | 2010-09-28 | 2010-09-29 | 2010-09-30 | 2010-10-01 | 2010-10-02 | 2010-10-03
| In Class | 2010-09-27: 2.5; 2010-09-29: 2.5; 2010-10-01: 2.5 | 7.5 |  | In Class | 2.5 |  | 2.5 |  | 2.5 |  |  | 7.5 |  | In Class | 2.5 |  | 2.5 |  |  |  |  | 5 |  | In Class | 2.5 |  | 2.5 |  | 2.5 |  |  | 7.5 |  | In Class |  |  | 2.5 |  | 2.5 |  |  | 5
| Team Meetings | 2010-09-27: 1.5; 2010-10-02: 1 | 2.5 |  | Team Meetings | 1.5 |  |  |  |  | 1 |  | 2.5 |  | Team Meetings | 1.5 | [6 empty] | 1.5 |  | Team Meetings | 1.5 |  |  |  |  | 1 |  | 2.5 |  | Team Meetings | 1.5 |  |  |  |  | 1 |  | 2.5
| Reading | 2010-09-29: 0.5; 2010-10-03: 1 | 1.5 |  | Reading |  | 1 |  |  | 1 |  | 1 | 3 |  | Reading | 1 | 1 | [5 empty] | 2 |  | Reading |  | 1 |  |  |  |  | 2 | 3 |  | Reading | 1 | [5 empty] | 1 | 2
| Homework | 2010-10-02: 2 | 2 |  | Homework | [6 empty] | 2 | 2 |  | Homework | [7 empty] | 0 |  | Homework | [5 empty] | 1 | 1 | 2 |  | Homework | 2 | [5 empty] | 1 | 3
| Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0
| Team Assignment | 2010-09-28: 0.5; 2010-10-03: 3 | 3.5 |  | Team Assignment | 1 | 0.5 | 0.5 |  | 2 |  | 1 | 5 |  | Team Assignment | 1 |  | 1 |  |  |  |  | 2 |  | Team Assignment |  |  | 0.5 |  |  |  | 3 | 3.5 |  | Team Assignment | [6 empty] | 2 | 2
| Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0
| Total | 4 | 0.5 | 3 | 0 | 2.5 | 3 | 4 | 17 |  | Total | 5 | 1.5 | 3 | 0 | 5.5 | 1 | 4 | 20 |  | Total | 6 | 1 | 3.5 | 0 | 0 | 0 | 0 | 10.5 |  | Total | 4 | 1 | 3 | 0 | 2.5 | 2 | 6 | 18.5 |  | Total | 4.5 | 0 | 2.5 | 0 | 2.5 | 1 | 4 | 14.5

## Actual-Week 4
Weekly Effort Recording Form W#4 | [9 empty] | Weekly Effort Recording Form W#4 | [9 empty] | Weekly Effort Recording Form W#4 | [9 empty] | Weekly Effort Recording Form W#4 | [9 empty] | Weekly Effort Recording Form W#4
Name: | Duong Nguyen | Starting Date: |  | 2010-10-04 | [5 empty] | Name: | Hien Nguyen | Starting Date: |  | 2010-10-04 | [5 empty] | Name: | Mung Nguyen | Starting Date: |  | 2010-10-04 | [5 empty] | Name: | Binh Huynh | Starting Date: |  | 2010-10-04 | [5 empty] | Name: | Manh Nguyen | Starting Date: |  | 2010-10-04
Course: | SMA | 2010-10-04 | 2010-10-05 | 2010-10-06 | 2010-10-07 | 2010-10-08 | 2010-10-09 | 2010-10-10 | Total | Course | SMA | 2010-10-04 | 2010-10-05 | 2010-10-06 | 2010-10-07 | 2010-10-08 | 2010-10-09 | 2010-10-10 | Total | Course | SMA | 2010-10-04 | 2010-10-05 | 2010-10-06 | 2010-10-07 | 2010-10-08 | 2010-10-09 | 2010-10-10 | Total | Course | SMA | 2010-10-04 | 2010-10-05 | 2010-10-06 | 2010-10-07 | 2010-10-08 | 2010-10-09 | 2010-10-10 | Total | Course: | SMA | 2010-10-04 | 2010-10-05 | 2010-10-06 | 2010-10-07 | 2010-10-08 | 2010-10-09 | 2010-10-10 | Total
| Task | 2010-10-04 | 2010-10-05 | 2010-10-06 | 2010-10-07 | 2010-10-08 | 2010-10-09 | 2010-10-10 |  |  | Task | 2010-10-04 | 2010-10-05 | 2010-10-06 | 2010-10-07 | 2010-10-08 | 2010-10-09 | 2010-10-10 |  |  | Task | 2010-10-04 | 2010-10-05 | 2010-10-06 | 2010-10-07 | 2010-10-08 | 2010-10-09 | 2010-10-10 |  |  | Task | 2010-10-04 | 2010-10-05 | 2010-10-06 | 2010-10-07 | 2010-10-08 | 2010-10-09 | 2010-10-10 |  |  | Task | 2010-10-04 | 2010-10-05 | 2010-10-06 | 2010-10-07 | 2010-10-08 | 2010-10-09 | 2010-10-10
| In Class | 2010-10-04: 2.5; 2010-10-06: 2.5; 2010-10-08: 2.5 | 7.5 |  | In Class | 2.5 |  | 2.5 |  | 2.5 |  |  | 7.5 |  | In Class | 2.5 |  | 2.5 |  | 2.5 |  |  | 7.5 |  | In Class |  |  | 2.5 |  | 2.5 |  |  | 5 |  | In Class | 2.5 |  |  |  | 2.5 |  |  | 5
| Team Meetings | 2010-10-04: 2; 2010-10-05: 2; 2010-10-06: 3; 2010-10-07: 3 | 10 |  | Team Meetings | 2 | 2 | 3 | 3 |  |  |  | 10 |  | Team Meetings | 2 | 2 | 3 | 3 |  |  |  | 10 |  | Team Meetings |  | 2 | 3 | 3 |  |  |  | 8 |  | Team Meetings | [7 empty] | 0
| Reading | 2010-10-04: 0.5; 2010-10-10: 1 | 1.5 |  | Reading |  | 1 |  |  | 0.5 |  | 2 | 3.5 |  | Reading |  |  |  |  | 1 |  |  | 1 |  | Reading |  | 1 |  |  | 1 | 1 |  | 3 |  | Reading | 2 | [6 empty] | 2
| Homework | 2010-10-10: 2 | 2 |  | Homework |  |  |  |  | 0.5 |  | 2 | 2.5 |  | Homework | [5 empty] | 1 | 1 | 2 |  | Homework | 2 | [6 empty] | 2 |  | Homework | 2 | [6 empty] | 2
| Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0
| Team Assignment | 2010-10-04: 0.5; 2010-10-05: 0.5; 2010-10-07: 0.5; 2010-10-10: 1 | 2.5 |  | Team Assignment | 1 | 2 | 2 | 0.5 | 0.5 |  | 1 | 7 |  | Team Assignment | 0.5 | 2 | [5 empty] | 2.5 |  | Team Assignment | 0.5 | 0.5 | 1 | 1.5 | 1 | 1 |  | 5.5 |  | Team Assignment |  |  |  |  | 1 |  |  | 1
| Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0
| Total | 5.5 | 2.5 | 5.5 | 3.5 | 2.5 | 0 | 4 | 23.5 |  | Total | 5.5 | 5 | 7.5 | 3.5 | 4 | 0 | 5 | 30.5 |  | Total | 5 | 4 | 5.5 | 3 | 3.5 | 1 | 1 | 23 |  | Total | 2.5 | 3.5 | 6.5 | 4.5 | 4.5 | 2 | 0 | 23.5 |  | Total | 6.5 | 0 | 0 | 0 | 3.5 | 0 | 0 | 10

## Acutal-Week 5
Weekly Effort Recording Form W#5 | [9 empty] | Weekly Effort Recording Form W#5 | [9 empty] | Weekly Effort Recording Form W#5 | [9 empty] | Weekly Effort Recording Form W#5 | [9 empty] | Weekly Effort Recording Form W#5
Name: | Duong Nguyen | Starting Date: |  | 2010-10-11 | [5 empty] | Name: | Hien Nguyen | Starting Date: |  | 2010-10-11 | [5 empty] | Name: | Binh Huynh | Starting Date: |  | 2010-10-11 | [5 empty] | Name: | Mung Nguyen | Starting Date: |  | 2010-10-11 | [5 empty] | Name: | Manh Nguyen | Starting Date: |  | 2010-10-11
Course | SMA | 2010-10-11 | 2010-10-12 | 2010-10-13 | 2010-10-14 | 2010-10-15 | 2010-10-16 | 2010-10-17 | Total | Course | SMA | 2010-10-11 | 2010-10-12 | 2010-10-13 | 2010-10-14 | 2010-10-15 | 2010-10-16 | 2010-10-17 | Total | Course | SMA | 2010-10-11 | 2010-10-12 | 2010-10-13 | 2010-10-14 | 2010-10-15 | 2010-10-16 | 2010-10-17 | Total | Course | SMA | 2010-10-11 | 2010-10-12 | 2010-10-13 | 2010-10-14 | 2010-10-15 | 2010-10-16 | 2010-10-17 | Total | Course | SMA | 2010-10-11 | 2010-10-12 | 2010-10-13 | 2010-10-14 | 2010-10-15 | 2010-10-16 | 2010-10-17 | Total
| Task | 2010-10-11 | 2010-10-12 | 2010-10-13 | 2010-10-14 | 2010-10-15 | 2010-10-16 | 2010-10-17 |  |  | Task | 2010-10-11 | 2010-10-12 | 2010-10-13 | 2010-10-14 | 2010-10-15 | 2010-10-16 | 2010-10-17 |  |  | Task | 2010-10-11 | 2010-10-12 | 2010-10-13 | 2010-10-14 | 2010-10-15 | 2010-10-16 | 2010-10-17 |  |  | Task | 2010-10-11 | 2010-10-12 | 2010-10-13 | 2010-10-14 | 2010-10-15 | 2010-10-16 | 2010-10-17 |  |  | Task | 2010-10-11 | 2010-10-12 | 2010-10-13 | 2010-10-14 | 2010-10-15 | 2010-10-16 | 2010-10-17
| In Class | 2010-10-11: 2.5; 2010-10-13: 2.5 | 5 |  | In Class | 2.5 |  | 2.5 |  |  |  |  | 5 |  | In Class | [7 empty] | 0 |  | In Class | 2.5 |  | 2.5 |  |  |  |  | 5 |  | In Class |  |  | 2.5 |  |  |  |  | 2.5
| Team Meetings | 2010-10-12: 2 | 2 |  | Team Meetings |  | 2 | [5 empty] | 2 |  | Team Meetings |  | 2 | [5 empty] | 2 |  | Team Meetings |  | 2 | [5 empty] | 2 |  | Team Meetings |  | 2 | [5 empty] | 2
| Reading | [7 empty] | 0 |  | Reading |  | 1 |  | 2 |  |  |  | 3 |  | Reading |  | 1 | 1 | 1 |  |  |  | 3 |  | Reading |  |  |  | 1 |  |  |  | 1 |  | Reading | 1 |  |  | 1 |  |  |  | 2
| Homework | [7 empty] | 0 |  | Homework | [7 empty] | 0 |  | Homework | [7 empty] | 0 |  | Homework | [7 empty] | 0 |  | Homework | 2 | [6 empty] | 2
| Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0 |  | Labs | [7 empty] | 0
| Team Assignment | 2010-10-11: 0.5; 2010-10-12: 0.5; 2010-10-13: 0.5; 2010-10-14: 1 | 2.5 |  | Team Assignment | 2 | 0.5 | 0.5 | 0.5 |  |  |  | 3.5 |  | Team Assignment | 1 | 0.5 | 1 | 1.5 |  |  |  | 4 |  | Team Assignment | 1 | [6 empty] | 1 |  | Team Assignment | 1 | 1 | 2 |  |  |  |  | 4
| Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0 |  | Meetings with Faculty | [7 empty] | 0
| Total | 3 | 2.5 | 3 | 1 | 0 | 0 | 0 | 9.5 |  | Total | 4.5 | 3.5 | 3 | 2.5 | 0 | 0 | 0 | 13.5 |  | Total | 1 | 3.5 | 2 | 2.5 | 0 | 0 | 0 | 9 |  | Total | 3.5 | 2 | 2.5 | 1 | 0 | 0 | 0 | 9 |  | Total | 4 | 3 | 4.5 | 1 | 0 | 0 | 0 | 12.5

## Analysis and Conclusion
Duong Nguyen
Week# | Analysis and Conclusion
1 | Làm việc tuần đầu nhẹ nhàng, sự ước tính về thời gian theo thực tế chính xác được 90%, lí do của sự sai lêch là do sự ước tính về những công việc bên ngoài có sự thay đổi về thời gian (giảm bớt)
2 | Làm việc tốn nhiều thời gian hơn so với dự tính 15% bời do tốn nhiều thời gian ở homework và team meeting. Cần kiểm soát thời gian trong các buổi meeting tốt hơn.
3 | Làm việc hiệu quả. Tuy đã thực hiện được đúng với tổng thời gian trong kế hoạch nhưng vẫn có sự sai lệch về thời gian trong từng nhiệm vụ của mỗi ngày.
4 | Làm việc tốn nhiều thời gian hơn so vớ dự định 20% bởi tuần này có lượng bài tập nhóm nhiều gấp đôi so với các tuần khác. Vượt quá 20% là chấp nhập được
5
6
7
8
9
10
11
12
13
14
15
16
17
Binh Huynh
Week# | Analysis and Conclusion
1 | Thời gian họp nhóm ngắn hơn so với kế hoạch ban đầu là 30 phút cho mỗi lần họp nhóm và họp 2 buổi so với kế hoạch 3 buổi/tuần. Bài team nhóm tuần khá nhẹ nhàng. Hiệu suất làm việc tốt
2 | Tham gia họp nhóm và tham gia lớp hoc ít hơn so với kế hoạch vì một số lí do cá nhân, thời gian đọc tài liệu và làm hw nhiều hơn so với dự tính vì tài liệu khá nhiều, có nhiều vấn đề xem xét
3 | Hiệu quả làm việc chưa cao, vì lí do sức khỏe. Khối lượng công việc nhiều, do vậy trễ lịch trình đã đặt ra
4
5
6
7
8
9
10
11
12
13
14
15
16
17
Hien Nguyen
Week# | Analysis and Conclusion
1 | Về Team Assignment 1, chuẩn bị tốt, họp ít hơn so với kế hoạch 1 buổi. Reading, đọc tài liệu tốt, gặp một só khó khăn về cách hiểu nguyên câu. Homework, không hiểu 1 câu hỏi
2 | Về Team Assignemt, chuẩn bị tốt, họp nhóm theo kế hoạch,tuy nhiên thời gian có tăng thêm do có vấn đề trong ban draft. Reading, chưa sắp xếp thời gian nhiều để đọc reading cho tuần sau. Homework, dựa trên việc tìm hiểu bài team,đã làm tốt homework
3 | Đầu Tuần không có Team Ass nhẹ nhàng. Bài đọc dễ hiểu,nên thời gian reading không giống như dự tính. Dự đoán thứ 6,7 sẽ bắt đầu như bình thường
Thứ 6 bắt đầu nhận 2 Team Assginment cùng bài homework nên công việc bắt đầu nhiều hơn, và sát với kế hoạch đặt ra từ trước
4 | Đầu tuần công việc 2 bài team vẫn còn, tuy nhiên gặp nhiều khó khăn,nên việc họp nhóm kéo dài hơn dự tính ban đầu.
5
6
7
8
9
10
11
12
13
14
15
16
17
Manh Nguyen
Week# | Analysis and Conclusion
1
2 | Tham gia các buổi học nhóm nhưng chua đóng góp được nhiều
3 | Chưa sắp sếp được thời gian làm home work và reading để thảo luận trong buổi học nhóm
4 | Không tham gia team vì 1 số lý do cá nhân . Tuần sau cần cố gắng tích cực hơn
5 | Có những đóng góp tích cực hơn cho team . Hoàn thành tương đối tốt nhiệm vụ được giao . Cần cố gắng hơn nữa
6
7
8
9
10
11
12
13
14
15
16
17
Mung Nguyen
Week# | Analysis and Conclusion
1
2 | Thời gian thực tế nhiều hơn kế hoạch 3 giờ nguyên nhân đó là tập trung nhiều thời gian để nghiên cứu team assignment , homework và test, cần tận dụng tốt thời gian để hoàn thành công việc đúng kế hoạch
3 | Tuần này team assignment nhẹ nhàng nên thời gian họp nhóm và reading ít hơn dự định.Mức độ chính xác của actual so với plan đề ra là 92,5%.
4 | Bắt đầu nhận 2 bài team assignment4 ,5 khối lượng công việc nhiều, thời gian họp nhóm kéo dài hơn so với dự định cụ thể plan là 4h nhưng actual là 5.5h.Cần phải sắp xếp thời gian tốt hơn để giải quyết mọi công việc
5 | Thời gian họp nhóm kéo dài hơn so với kế hoạch do chưa thống nhất được ý kiến của các thành viên trong nhóm về ý tưởng bài tập, một số thành viên chưa thật sự đúng giờ. Cần sửa chữa
6
7
8
9
10
11
12
13
14
15
16
17

## Effort Summary
Year | Semester | Course | Task | Week | Day | Planned/Actual | Hours | Team# | Student
2010 | 1 | SMA | In Class | 1 | Monday | Planned | 2 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 1 | Tuesday | Planned | 0.5 | 1 | Duong Nguyen
2010 | 1 | SMA | In Class | 1 | Wednesday | Planned | 2 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Assignment | 1 | Thusday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | In Class | 1 | Friday | Planned | 2 | 1 | Duong Nguyen
2010 | 1 | SMA | Homework | 1 | Friday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Assignment | 1 | Friday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 1 | Saturday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Homework | 1 | Saturday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Assignment | 1 | Saturday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Reading | 1 | Sunday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Homework | 1 | Sunday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Assignment | 1 | Sunday | Planned | 1.5 | 1 | Duong Nguyen
2010 | 1 | SMA | In Class | 1 | Monday | Actual | 2 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 1 | Tuesday | Actual | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | In Class | 1 | Wednesday | Actual | 2 | 1 | Duong Nguyen
2010 | 1 | SMA | Reading | 1 | Thusday | Actual | 1.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Assignment | 1 | Thusday | Actual | 0.5 | 1 | Duong Nguyen
2010 | 1 | SMA | In Class | 1 | Friday | Actual | 2 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Assignment | 1 | Friday | Actual | 1.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 1 | Saturday | Actual | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Homework | 1 | Sunday | Actual | 4 | 1 | Duong Nguyen
2010 | 1 | SMA | In Class | 2 | Monday | Planned | 2.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 2 | Monday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Reading | 2 | Monday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 2 | Tuesday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Homework | 2 | Tuesday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Assignment | 2 | Tuesday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | In Class | 2 | Wednesday | Planned | 2.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 2 | Thusday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Assignment | 2 | Thusday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | In Class | 2 | Friday | Planned | 2.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Reading | 2 | Friday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 2 | Saturday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Homework | 2 | Saturday | Planned | 2 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Assignment | 2 | Saturday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Assignment | 2 | Friday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Homework | 2 | Sunday | Planned | 2 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Assignment | 2 | Sunday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | In Class | 2 | Monday | Actual | 2.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 2 | Monday | Actual | 1.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Reading | 2 | Monday | Actual | 1.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 2 | Tuesday | Actual | 1.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Homework | 2 | Tuesday | Actual | 1.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Assignment | 2 | Tuesday | Actual | 1.5 | 1 | Duong Nguyen
2010 | 1 | SMA | In Class | 2 | Wednesday | Actual | 2.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 2 | Thusday | Actual | 3 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Assignment | 2 | Thusday | Actual | 0.5 | 1 | Duong Nguyen
2010 | 1 | SMA | In Class | 2 | Friday | Actual | 2.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Assignment | 2 | Friday | Actual | 3 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 2 | Saturday | Actual | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Reading | 2 | Saturday | Actual | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Homework | 2 | Saturday | Actual | 2.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Homework | 2 | Sunday | Actual | 2 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 1 | Monday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Meetings | 1 | Friday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 1 | Tuesday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 1 | Wednesday | Planned | 0 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 1 | Wednesday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 1 | Friday | Planned | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 1 | Sunday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 1 | Monday | Planned | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 1 | Wednesday | Planned | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 1 | Friday | Planned | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Homework | 1 | Sunday | Planned | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 1 | Monday | Actual | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 1 | Wednesday | Actual | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 1 | Friday | Actual | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Meetings | 1 | Monday | Actual | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Meetings | 1 | Friday | Actual | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 1 | Tuesday | Actual | 0.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 1 | Wednesday | Actual | 0 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 1 | Thursday | Actual | 0.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 1 | Friday | Actual | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 1 | Sunday | Actual | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | Homework | 1 | Sunday | Actual | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Meetings | 2 | Monday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Meetings | 2 | Tuesday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Meetings | 2 | Thursday | Planned | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Meetings | 2 | Saturday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 2 | Tuesday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 2 | Wednesday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 2 | Thursday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 2 | Saturday | Planned | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 2 | Sunday | Planned | 3 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 2 | Monday | Planned | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 2 | Wednesday | Planned | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 2 | Friday | Planned | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Homework | 2 | Monday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Homework | 2 | Sunday | Planned | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 2 | Monday | Actual | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 2 | Wednesday | Actual | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 2 | Friday | Actual | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Meetings | 2 | Monday | Actual | 1.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Meetings | 2 | Tuesday | Actual | 1.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Meetings | 2 | Thursday | Actual | 3 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 2 | Tuesday | Actual | 0.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 2 | Wednesday | Actual | 0.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 2 | Thursday | Actual | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Homework | 2 | Monday | Actual | 0.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Homework | 2 | Thursday | Actual | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 1 | Monday | Planned | 2.5 | 1 | Binh Huynh
2010 | 1 | SMA | In Class | 1 | Wednesday | Planned | 2.5 | 1 | Binh Huynh
2010 | 1 | SMA | In Class | 1 | Friday | Planned | 2.5 | 1 | Binh Huynh
2010 | 1 | SMA | Team Meetings | 1 | Tuesday | Planned | 1.5 | 1 | Binh Huynh
2010 | 1 | SMA | Team Meetings | 1 | Thursday | Planned | 1.5 | 1 | Binh Huynh
2010 | 1 | SMA | Team Meetings | 1 | Saturday | Planned | 1.5 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 1 | Tuesday | Planned | 1.5 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 1 | Thursday | Planned | 1.5 | 1 | Binh Huynh
2010 | 1 | SMA | In Class | 1 | Monday | Actual | 2.5 | 1 | Binh Huynh
2010 | 1 | SMA | In Class | 1 | Wednesday | Actual | 2.5 | 1 | Binh Huynh
2010 | 1 | SMA | In Class | 1 | Friday | Actual | 2.5 | 1 | Binh Huynh
2010 | 1 | SMA | Team Meetings | 1 | Tuesday | Actual | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Team Meetings | 1 | Saturday | Actual | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 1 | Thursday | Actual | 1 | 1 | Binh Huynh
2010 | 1 | SMA | In Class | 2 | Monday | Planned | 2.5 | 1 | Binh Huynh
2010 | 1 | SMA | In Class | 2 | Wednesday | Planned | 2.5 | 1 | Binh Huynh
2010 | 1 | SMA | In Class | 2 | Friday | Planned | 2.5 | 1 | Binh Huynh
2010 | 1 | SMA | Team Meetings | 2 | Tuesday | Planned | 1.5 | 1 | Binh Huynh
2010 | 1 | SMA | Team Meetings | 2 | Thursday | Planned | 1.5 | 1 | Binh Huynh
2010 | 1 | SMA | Team Meetings | 2 | Saturday | Planned | 1.5 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 2 | Monday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 2 | Thursday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 2 | Sunday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Homework | 2 | Wednesday | Planned | 2 | 1 | Binh Huynh
2010 | 1 | SMA | Others | 2 | Thursday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | In Class | 2 | Wednesday | Actual | 2.5 | 1 | Binh Huynh
2010 | 1 | SMA | In Class | 2 | Friday | Actual | 2.5 | 1 | Binh Huynh
2010 | 1 | SMA | Team Meetings | 2 | Tuesday | Actual | 1.5 | 1 | Binh Huynh
2010 | 1 | SMA | Team Meetings | 2 | Thursday | Actual | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 2 | Monday | Actual | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 2 | Tuesday | Actual | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 2 | Wednesday | Actual | 1.5 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 2 | Thursday | Actual | 2 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 2 | Friday | Actual | 1.3 | 1 | Binh Huynh
2010 | 1 | SMA | Homework | 2 | Tuesday | Actual | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Homework | 2 | Thursday | Actual | 3 | 1 | Binh Huynh
2010 | 1 | SMA | Team Assignment | 2 | Monday | Actual | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Team Assignment | 2 | Friday | Actual | 3 | 1 | Binh Huynh
2010 | 1 | SMA | In Class | 1 | Monday | Actual | 0 | 1 | Mung Nguyen
2010 | 1 | SMA | Reading | 1 | Tuesday | Actual | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 1 | Tuesday | Actual | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | In Class | 1 | Wednesday | Actual | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Team assignment | 1 | Wednesday | Actual | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Reading | 1 | Thursday | Actual | 1.5 | 1 | Mung Nguyen
2010 | 1 | SMA | In Class | 1 | Friday | Actual | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Team assignment | 1 | Friday | Actual | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Team assignment | 1 | Saturday | Actual | 3 | 1 | Mung Nguyen
2010 | 1 | SMA | Homework | 1 | Monday | Planned | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 1 | Tuesday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Reading | 1 | Tuesday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | In Class | 1 | Wednesday | Planned | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Team assignment | 1 | Wednesday | Planned | 0 | 1 | Mung Nguyen
2010 | 1 | SMA | Reading | 1 | Thursday | Planned | 1.5 | 1 | Mung Nguyen
2010 | 1 | SMA | In Class | 1 | Friday | Planned | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Team assignment | 1 | Friday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Team assignment | 1 | Saturday | Planned | 2 | 1 | Mung Nguyen
2010 | 1 | SMA | In Class | 2 | Monday | Planned | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 2 | Tuesday | Planned | 2 | 1 | Mung Nguyen
2010 | 1 | SMA | Reading | 2 | Tuesday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | In Class | 2 | Wednesday | Planned | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Reading | 2 | Wednesday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Homework | 2 | Wednesday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 2 | Thursday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Reading | 2 | Thursday | Planned | 1.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Homework | 2 | Thursday | Planned | 2 | 1 | Mung Nguyen
2010 | 1 | SMA | In Class | 2 | Friday | Planned | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Team assignment | 2 | Friday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 2 | Saturday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Reading | 2 | Saturday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Team assignment | 2 | Saturday | Planned | 3 | 1 | Mung Nguyen
2010 | 1 | SMA | In Class | 2 | Monday | Actual | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 2 | Monday | Actual | 1.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 2 | Tuesday | Actual | 1.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Reading | 2 | Tuesday | Actual | 2 | 1 | Mung Nguyen
2010 | 1 | SMA | Reading | 2 | Wednesday | Actual | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Homework | 2 | Wednesday | Actual | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | In Class | 2 | Wednesday | Actual | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Homework | 2 | Thursday | Actual | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Team assignment | 2 | Thursday | Actual | 2 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 2 | Thursday | Actual | 3 | 1 | Mung Nguyen
2010 | 1 | SMA | In Class | 2 | Friday | Actual | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 2 | Saturday | Actual | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Homework | 2 | Saturday | Actual | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Homework | 2 | Sunday | Actual | 2 | 1 | Mung Nguyen
2010 | 1 | SMA | In Class | 3 | Monday | Planned | 2.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 3 | Monday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Team assignment | 3 | Tuesday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 3 | Tuesday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | In Class | 3 | Wednesday | Planned | 2.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Reading | 3 | Wednesday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | In Class | 3 | Friday | Planned | 2.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Reading | 3 | Friday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Team assignment | 3 | Saturday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 3 | Saturday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Homework | 3 | Saturday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Team assignment | 3 | Sunday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Homework | 3 | Sunday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | In Class | 3 | Monday | Actual | 2.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 3 | Monday | Actual | 1.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team assignment | 3 | Tuesday | Actual | 0.5 | 1 | Duong Nguyen
2010 | 1 | SMA | In Class | 3 | Monday | Planned | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 3 | Monday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Team assignment | 3 | Monday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 3 | Tuesday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Reading | 3 | Tuesday | Planned | 2 | 1 | Mung Nguyen
2010 | 1 | SMA | In Class | 3 | Wednesday | Planned | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Reading | 3 | Wednesday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 3 | Thursday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Team assignment | 3 | Thursday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | In Class | 3 | Friday | Planned | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Team assignment | 3 | Friday | Planned | 3 | 1 | Mung Nguyen
2010 | 1 | SMA | Reading | 3 | Friday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 3 | Saturday | Planned | 0.5 | 1 | Mung Nguyen
2010 | 1 | SMA | In Class | 3 | Monday | Actual | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 3 | Monday | Actual | 1.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Reading | 3 | Tuesday | Actual | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 2 | Saturday | Actual | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Homework | 2 | Sunday | Actual | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Meetings | 3 | Monday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Meetings | 3 | Tuesday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Meetings | 3 | Thursday | Planned | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Meetings | 3 | Saturday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 3 | Tuesday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 3 | Wednesday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 3 | Thursday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 3 | Saturday | Planned | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 3 | Sunday | Planned | 3 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 3 | Monday | Planned | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 3 | Wednesday | Planned | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 3 | Friday | Planned | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Homework | 3 | Sunday | Planned | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | Homework | 3 | Friday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Assignment | 3 | Monday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Assignment | 3 | Wednesday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Assignment | 3 | Friday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Meetings | 3 | Monday | Actual | 1.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Meetings | 3 | Saturday | Actual | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Assignment | 3 | Monday | Actual | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 3 | Tuesday | Actual | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 3 | Friday | Actual | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 3 | Sunday | Actual | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 3 | Monday | Actual | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 3 | Wednesday | Actual | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 3 | Friday | Actual | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Assignment | 3 | Thursday | Actual | 0.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Assignment | 3 | Wednesday | Actual | 0.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Assignment | 3 | Friday | Actual | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Assignment | 3 | Sunday | Actual | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Homework | 3 | Sunday | Actual | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 3 | Monday | Planned | 2.3 | 1 | Binh Huynh
2010 | 1 | SMA | In Class | 3 | Wednesday | Planned | 2.3 | 1 | Binh Huynh
2010 | 1 | SMA | In Class | 3 | Friday | Planned | 2.3 | 1 | Binh Huynh
2010 | 1 | SMA | Team Meetings | 3 | Tuesday | Planned | 1.3 | 1 | Binh Huynh
2010 | 1 | SMA | Team Meetings | 3 | Thursday | Planned | 1.3 | 1 | Binh Huynh
2010 | 1 | SMA | Team Meetings | 3 | Saturday | Planned | 1.3 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 3 | Monday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 3 | Tuesday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 3 | Thursday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 3 | Saturday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 3 | Sunday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Homework | 3 | Webnesday | Planned | 2 | 1 | Binh Huynh
2010 | 1 | SMA | Team assignment | 3 | Monday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Team assignment | 3 | Wednesday | Planned | 2 | 1 | Binh Huynh
2010 | 1 | SMA | Team assignment | 3 | Friday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | In Class | 3 | Monday | Actual | 2.5 | 1 | Binh Huynh
2010 | 1 | SMA | Team Meetings | 3 | Monday | Actual | 1.5 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 3 | Monday | Actual | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 3 | Tuesday | Actual | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Team assignment | 3 | Monday | Actual | 1 | 1 | Binh Huynh
2010 | 1 | SMA | In Class | 3 | Wednesday | Actual | 2.5 | 1 | Binh Huynh
2010 | 1 | SMA | Team assignment | 3 | Wednesday | Actual | 1 | 1 | Binh Huynh
2010 | 1 | SMA | In Class | 3 | Wednesday | Actual | 2.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Reading | 3 | Wednesday | Actual | 0.5 | 1 | Duong Nguyen
2010 | 1 | SMA | In Class | 3 | Wednesday | Actual | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Team assignment | 3 | Wednesday | Actual | 0.5 | 1 | Mung Nguyen
2010 | 1 | SMA | In Class | 3 | Friday | Actual | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 3 | Saturday | Actual | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Homework | 3 | Saturday | Actual | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Reading | 3 | Sunday | Actual | 2 | 1 | Mung Nguyen
2010 | 1 | SMA | Homework | 3 | Sunday | Actual | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Assignment | 3 | Sunday | Actual | 3 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Monday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Tuesday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Thursday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Saturday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 4 | Tuesday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 4 | Wednesday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 4 | Thursday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 4 | Saturday | Planned | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 4 | Sunday | Planned | 3 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 4 | Monday | Planned | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 4 | Wednesday | Planned | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 4 | Friday | Planned | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Homework | 4 | Sunday | Planned | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | Homework | 4 | Friday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Assignment | 4 | Monday | Planned | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Assignment | 4 | Wednesday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Assignment | 4 | Friday | Planned | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 3 | Friday | Actual | 2.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 3 | Saturday | Actual | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Homework | 3 | Saturday | Actual | 2 | 1 | Duong Nguyen
2010 | 1 | SMA | Reading | 3 | Sunday | Actual | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Team assignment | 3 | Sunday | Actual | 3 | 1 | Duong Nguyen
2010 | 1 | SMA | In Class | 4 | Monday | Planned | 2.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Monday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Tuesday | Planned | 1.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team assignment | 4 | Tuesday | Planned | 0.5 | 1 | Duong Nguyen
2010 | 1 | SMA | In Class | 4 | Wednesday | Planned | 2.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team assignment | 4 | Wednesday | Planned | 1.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Thursday | Planned | 1.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team assignment | 4 | Thursday | Planned | 0.5 | 1 | Duong Nguyen
2010 | 1 | SMA | In Class | 4 | Friday | Planned | 2.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Saturday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Homework | 4 | Saturday | Planned | 2 | 1 | Duong Nguyen
2010 | 1 | SMA | Reading | 4 | Sunday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Team assignment | 4 | Sunday | Planned | 2 | 1 | Duong Nguyen
2010 | 1 | SMA | In Class | 4 | Monday | Actual | 2.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Monday | Actual | 2 | 1 | Duong Nguyen
2010 | 1 | SMA | Reading | 4 | Monday | Actual | 0.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Assignment | 4 | Monday | Actual | 0.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Tuesday | Actual | 2 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Assignment | 4 | Tuesday | Actual | 0.5 | 1 | Duong Nguyen
2010 | 1 | SMA | In Class | 4 | Monday | Actual | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 4 | Wednesday | Actual | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 4 | Friday | Actual | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Monday | Actual | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Assignment | 4 | Monday | Actual | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Tuesday | Actual | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Wednesday | Actual | 3 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Thursday | Actual | 3 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 4 | Tuesday | Actual | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 4 | Friday | Actual | 0.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 4 | Sunday | Actual | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | Homework | 4 | Friday | Actual | 0.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Homework | 4 | Sunday | Actual | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Assignment | 4 | Tuesday | Actual | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Assignment | 4 | Wednesday | Actual | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Assignment | 4 | Thursday | Actual | 0.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Assignment | 4 | Friday | Actual | 0.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Assignment | 4 | Sunday | Actual | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 4 | Monday | Planned | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Monday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Tuesday | Planned | 1.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Assignment | 4 | Tuesday | Planned | 2 | 1 | Mung Nguyen
2010 | 1 | SMA | In Class | 4 | Wednesday | Planned | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Thursday | Planned | 1.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Reading | 4 | Thursday | Planned | 2 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Assignment | 4 | Thursday | Planned | 0.5 | 1 | Mung Nguyen
2010 | 1 | SMA | In Class | 4 | Friday | Planned | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Saturday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Homework | 4 | Saturday | Planned | 2 | 1 | Mung Nguyen
2010 | 1 | SMA | Homework | 4 | Sunday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Reading | 4 | Sunday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | In Class | 4 | Monday | Actual | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Monday | Actual | 2 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Assignment | 4 | Monday | Actual | 0.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Tuesday | Actual | 2 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Assignment | 4 | Tuesday | Actual | 2 | 1 | Mung Nguyen
2010 | 1 | SMA | In Class | 4 | Wednesday | Actual | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Wednesday | Actual | 3 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Thursday | Actual | 3 | 1 | Mung Nguyen
2010 | 1 | SMA | In Class | 4 | Friday | Actual | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Reading | 4 | Friday | Actual | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Homework | 4 | Saturday | Actual | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Homework | 4 | Sunday | Actual | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | In Class | 4 | Monday | Planned | 2.5 | 1 | Binh Huynh
2010 | 1 | SMA | In Class | 4 | Wednesday | Planned | 2.5 | 1 | Binh Huynh
2010 | 1 | SMA | In Class | 4 | Friday | Planned | 2.5 | 1 | Binh Huynh
2010 | 1 | SMA | Team Meetings | 4 | Monday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Team Meetings | 4 | Tuesday | Planned | 1.5 | 1 | Binh Huynh
2010 | 1 | SMA | Team Meetings | 4 | Thursday | Planned | 1.5 | 1 | Binh Huynh
2010 | 1 | SMA | Team Meetings | 4 | Saturday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 4 | Wednesday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 4 | Thursday | Planned | 2 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 4 | Sunday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Homework | 4 | Friday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Team assignment | 4 | Tuesday | Planned | 2 | 1 | Binh Huynh
2010 | 1 | SMA | Team assignment | 4 | Thursday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | In Class | 4 | Wednesday | Actual | 2.5 | 1 | Binh Huynh
2010 | 1 | SMA | Team Meetings | 4 | Tuesday | Actual | 2 | 1 | Binh Huynh
2010 | 1 | SMA | Team Meetings | 4 | Wednesday | Actual | 3 | 1 | Binh Huynh
2010 | 1 | SMA | Team Meetings | 4 | Thursday | Actual | 3 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 4 | Tuesday | Actual | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Homework | 4 | Monday | Actual | 2 | 1 | Binh Huynh
2010 | 1 | SMA | Team assignment | 4 | Monday | Actual | 0.5 | 1 | Binh Huynh
2010 | 1 | SMA | Team assignment | 4 | Tuesday | Actual | 0.5 | 1 | Binh Huynh
2010 | 1 | SMA | In Class | 4 | Wednesday | Actual | 2.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Wednesday | Actual | 3 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Thursday | Actual | 3 | 1 | Duong Nguyen
2010 | 1 | SMA | Team assignment | 4 | Thursday | Actual | 0.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Monday | Planned | 1 | 1 | Manh Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Tuesday | Planned | 1 | 1 | Manh Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Thursday | Planned | 1 | 1 | Manh Nguyen
2010 | 1 | SMA | Team Meetings | 4 | Saturday | Planned | 1 | 1 | Manh Nguyen
2010 | 1 | SMA | Reading | 4 | Tuesday | Planned | 1 | 1 | Manh Nguyen
2010 | 1 | SMA | Reading | 4 | Wednesday | Planned | 1 | 1 | Manh Nguyen
2010 | 1 | SMA | Reading | 4 | Thursday | Planned | 1 | 1 | Manh Nguyen
2010 | 1 | SMA | Reading | 4 | Saturday | Planned | 2 | 1 | Manh Nguyen
2010 | 1 | SMA | Reading | 4 | Sunday | Planned | 3 | 1 | Manh Nguyen
2010 | 1 | SMA | In Class | 4 | Monday | Planned | 2.5 | 1 | Manh Nguyen
2010 | 1 | SMA | In Class | 4 | Wednesday | Planned | 2.5 | 1 | Manh Nguyen
2010 | 1 | SMA | In Class | 4 | Friday | Planned | 2.5 | 1 | Manh Nguyen
2010 | 1 | SMA | Homework | 4 | Sunday | Planned | 2 | 1 | Manh Nguyen
2010 | 1 | SMA | Homework | 4 | Friday | Planned | 1 | 1 | Manh Nguyen
2010 | 1 | SMA | Team Assignment | 4 | Monday | Planned | 2 | 1 | Manh Nguyen
2010 | 1 | SMA | Team Assignment | 4 | Wednesday | Planned | 1 | 1 | Manh Nguyen
2010 | 1 | SMA | Team Assignment | 4 | Friday | Planned | 2 | 1 | Manh Nguyen
2010 | 1 | SMA | In Class | 4 | Monday | Actual | 2.5 | 1 | Manh Nguyen
2010 | 1 | SMA | Reading | 4 | Monday | Actual | 2 | 1 | Manh Nguyen
2010 | 1 | SMA | Homework | 4 | Monday | Actual | 2 | 1 | Manh Nguyen
2010 | 1 | SMA | In Class | 4 | Friday | Actual | 2.5 | 1 | Manh Nguyen
2010 | 1 | SMA | Team Assignment | 4 | Friday | Actual | 1 | 1 | Manh Nguyen
2010 | 1 | SMA | Team Meetings | 5 | Tuesday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Meetings | 5 | Thursday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Meetings | 5 | Saturday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 5 | Tuesday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 5 | Thursday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 5 | Sunday | Planned | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 5 | Monday | Planned | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 5 | Wednesday | Planned | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 5 | Friday | Planned | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Homework | 5 | Sunday | Planned | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | Homework | 5 | Friday | Planned | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Assignment | 5 | Monday | Planned | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Assignment | 5 | Wednesday | Planned | 0.5 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 5 | Monday | Actual | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 5 | Wednesday | Actual | 2.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Meetings | 5 | Thursday | Actual | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Assignment | 5 | Monday | Actual | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Assignment | 5 | Tuesday | Actual | 0.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Assignment | 5 | Wednesday | Actual | 0.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Team Assignment | 5 | Thursday | Actual | 0.5 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 5 | Tuesday | Actual | 1 | 1 | Hien Nguyen
2010 | 1 | SMA | Reading | 5 | Thursday | Actual | 2 | 1 | Hien Nguyen
2010 | 1 | SMA | In Class | 4 | Friday | Actual | 2.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Reading | 4 | Sunday | Actual | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Homework | 4 | Sunday | Actual | 2 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Assignment | 4 | Sunday | Actual | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | In Class | 5 | Monday | Planned | 2.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Assignment | 5 | Monday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 5 | Tuesday | Planned | 1.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Assignment | 5 | Tuesday | Planned | 0.5 | 1 | Duong Nguyen
2010 | 1 | SMA | In Class | 5 | Wednesday | Planned | 2.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 5 | Thursday | Planned | 1.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Assignment | 5 | Thursday | Planned | 0.5 | 1 | Duong Nguyen
2010 | 1 | SMA | In Class | 5 | Friday | Planned | 2.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Reading | 5 | Friday | Planned | 2 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Assignment | 5 | Friday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 5 | Saturday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | Homework | 5 | Saturday | Planned | 2 | 1 | Duong Nguyen
2010 | 1 | SMA | Homework | 5 | Sunday | Planned | 0.5 | 1 | Duong Nguyen
2010 | 1 | SMA | Team Assignment | 5 | Sunday | Planned | 1 | 1 | Duong Nguyen
2010 | 1 | SMA | In Class | 5 | Monday | Actual | 2.5 | 2 | Duong Nguyen
2010 | 1 | SMA | Team Assignment | 5 | Monday | Actual | 0.5 | 3 | Duong Nguyen
2010 | 1 | SMA | Team Meetings | 5 | Tuesday | Actual | 2 | 4 | Duong Nguyen
2010 | 1 | SMA | Team Assignment | 5 | Tuesday | Actual | 0.5 | 5 | Duong Nguyen
2010 | 1 | SMA | In Class | 5 | Wednesday | Actual | 2.5 | 6 | Duong Nguyen
2010 | 1 | SMA | Team Assignment | 5 | Wednesday | Actual | 0.5 | 7 | Duong Nguyen
2010 | 1 | SMA | Team Assignment | 5 | Thursday | Actual | 1 | 8 | Duong Nguyen
2010 | 1 | SMA | In Class | 5 | Monday | Planned | 2.5 | 1 | Manh Nguyen
2010 | 1 | SMA | Team Assignment | 5 | Monday | Planned | 1 | 1 | Manh Nguyen
2010 | 1 | SMA | Team Meetings | 5 | Tuesday | Planned | 1.5 | 1 | Manh Nguyen
2010 | 1 | SMA | Team Assignment | 5 | Tuesday | Planned | 0.5 | 1 | Manh Nguyen
2010 | 1 | SMA | In Class | 5 | Wednesday | Planned | 2.5 | 1 | Manh Nguyen
2010 | 1 | SMA | Team Meetings | 5 | Thursday | Planned | 1.5 | 1 | Manh Nguyen
2010 | 1 | SMA | Team Assignment | 5 | Thursday | Planned | 0.5 | 1 | Manh Nguyen
2010 | 1 | SMA | In Class | 5 | Friday | Planned | 2.5 | 1 | Manh Nguyen
2010 | 1 | SMA | Reading | 5 | Friday | Planned | 2 | 1 | Manh Nguyen
2010 | 1 | SMA | Team Assignment | 5 | Friday | Planned | 1 | 1 | Manh Nguyen
2010 | 1 | SMA | Team Meetings | 5 | Saturday | Planned | 1 | 1 | Manh Nguyen
2010 | 1 | SMA | Homework | 5 | Saturday | Planned | 2 | 1 | Manh Nguyen
2010 | 1 | SMA | Homework | 5 | Sunday | Planned | 0.5 | 1 | Manh Nguyen
2010 | 1 | SMA | Team Assignment | 5 | Sunday | Planned | 1 | 1 | Manh Nguyen
2010 | 1 | SMA | In Class | 5 | Monday | Actual | 2.5 | 1 | Manh Nguyen
2010 | 1 | SMA | Team Meetings | 5 | Tuesday | Actual | 2 | 1 | Manh Nguyen
2010 | 1 | SMA | Reading | 5 | Monday | Actual | 1 | 1 | Manh Nguyen
2010 | 1 | SMA | Reading | 5 | Thursday | Actual | 1 | 1 | Manh Nguyen
2010 | 1 | SMA | Team assignment | 5 | Monday | Actual | 1 | 1 | Manh Nguyen
2010 | 1 | SMA | Team assignment | 5 | Tuesday | Actual | 1 | 1 | Manh Nguyen
2010 | 1 | SMA | Team assignment | 5 | Wednesday | Actual | 2 | 1 | Manh Nguyen
2010 | 1 | SMA | Team Assignment | 5 | Monday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | In Class | 5 | Monday | Planned | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 5 | Tuesday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Reading | 5 | Tuesday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | In Class | 5 | Wednesday | Planned | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 5 | Thursday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Reading | 5 | Thursday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | In Class | 5 | Friday | Planned | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 5 | Saturday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Homework | 5 | Saturday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Reading | 5 | Sunday | Planned | 2 | 1 | Mung Nguyen
2010 | 1 | SMA | Homework | 5 | Sunday | Planned | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | In Class | 5 | Monday | Actual | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Assignment | 5 | Monday | Actual | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Meetings | 5 | Tuesday | Actual | 2 | 1 | Mung Nguyen
2010 | 1 | SMA | In Class | 5 | Wednesday | Actual | 2.5 | 1 | Mung Nguyen
2010 | 1 | SMA | Reading | 5 | Thursday | Actual | 1 | 1 | Mung Nguyen
2010 | 1 | SMA | Team Assignment | 4 | Wednesday | Actual | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Team Assignment | 4 | Thursday | Actual | 1.5 | 1 | Binh Huynh
2010 | 1 | SMA | In Class | 4 | Friday | Actual | 2.5 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 4 | Friday | Actual | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Team Assignment | 4 | Friday | Actual | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 4 | Saturday | Actual | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Team Assignment | 4 | Saturday | Actual | 1 | 1 | Binh Huynh
2010 | 1 | SMA | In Class | 5 | Monday | Planned | 2.5 | 1 | Binh Huynh
2010 | 1 | SMA | Team Meetings | 5 | Monday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Team Assignment | 5 | Monday | Planned | 2 | 1 | Binh Huynh
2010 | 1 | SMA | Team Meetings | 5 | Tuesday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 5 | Tuesday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | In Class | 5 | Wednesday | Planned | 2.5 | 1 | Binh Huynh
2010 | 1 | SMA | Team Assignment | 5 | Wednesday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Team Meetings | 5 | Thursday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 5 | Thursday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Team Assignment | 5 | Thursday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | In Class | 5 | Friday | Planned | 2.5 | 1 | Binh Huynh
2010 | 1 | SMA | Team Assignment | 5 | Friday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Team Meetings | 5 | Saturday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 5 | Saturday | Planned | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 5 | Sunday | Planned | 2 | 1 | Binh Huynh
2010 | 1 | SMA | Homework | 5 | Sunday | Planned | 2 | 1 | Binh Huynh
2010 | 1 | SMA | Team Assignment | 5 | Monday | Actual | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Team Meetings | 5 | Tuesday | Actual | 2 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 5 | Tuesday | Actual | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Team Assignment | 5 | Tuesday | Actual | 0.5 | 1 | Binh Huynh
2010 | 1 | SMA | In Class | 5 | Wednesday | Actual | 2.5 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 5 | Wednesday | Actual | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Team Assignment | 5 | Wednesday | Actual | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Reading | 5 | Thursday | Actual | 1 | 1 | Binh Huynh
2010 | 1 | SMA | Team Assignment | 5 | Thursday | Actual | 1.5 | 1 | Binh Huynh

## Pivot Table
Student | Binh Huynh
Sum of Hours
Year | Week | Planned/Actual | Task | Total
2010 | 5 | Actual | In Class | 2.5
|  |  | Reading | 3
|  |  | Team Meetings | 2
|  |  | Team Assignment | 4
|  | Actual Total |  | 11.5
|  | Planned | Homework | 2
|  |  | In Class | 7.5
|  |  | Reading | 5
|  |  | Team Meetings | 4
|  |  | Team Assignment | 5
|  | Planned Total |  | 23.5
| 5 Total |  |  | 35
2010 Total |  |  |  | 35
Grand Total |  |  |  | 35

## Weekly Totals (hidden)
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15
| 9/13 - 9/19 | 9/20 - 9/26 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Read Plan of Attack | 1900-01-05 | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | 0 | 1900-01-01 12:00 | 0 | 1900-01-01 12:00 | 0 | 1900-01-01 12:00 | 0 | 0 | 1900-01-01 12:00
Task research | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 12:00 | 1899-12-31 12:00 | 0 | 1900-01-02 | 0 | 1899-12-31 | 0 | 1899-12-31 12:00
Task outline preparation | 1900-01-03 | 0 | 0 | 0 | 0 | 0 | 1900-01-03 | 1899-12-31 | 0 | 0 | 0 | 0 | 1899-12-31 | 0 | 0
Prepare individual deliverable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 12:00 | 0 | 0 | 0 | 1900-01-01 12:00 | 1900-01-01 | 0
Integrate group deliverable | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rework deliverable | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
Class meetings | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Team meetings | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Other meetings | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Readings | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Prepare effort log | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Respond to e-mail | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
Manage school related information | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Peer Reviews | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Update Twiki | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Weekly Totals | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!