## Sheet1
Scheduled W#2
Course | SMA |  |  | Starting Date: |  | 2012-02-20
|  |  |  | 2012-02-20 | 2012-02-21 | 2012-02-22 | 2012-02-23 | 2012-02-24 | 2012-02-25 | 2012-02-26
Assignment # | Sub-Leader | Task name | Assign to | 2012-02-20 | 2012-02-21 | 2012-02-22 | 2012-02-23 | 2012-02-24 | 2012-02-25 | 2012-02-26
1 + 2 | Le Dinh Thach Huyen | 1. Meeting 1 (Ass 1) | All | x
|  | 2. Do teamworks (Ass 1) | All | x | x | x
|  | 3. Read ABC system and Viking project references (Ass 2) | All |  | x | x
|  | 4. Meeting 2 (finish Ass 1, start Ass 2) | All |  |  | x
|  | 5. Do teamworks (Ass 2) | All |  |  | x | x
|  | 6. Meeting 3 (Ass 2) | All |  |  |  | x
|  | 7. Do teamworks (Ass 2) | All |  |  |  | x | x
|  | 8. Meeting 4 (Ass 2) | All |  |  |  |  | x
|  | 9. Make presentation file | Member |  |  |  |  | x
|  | 10. Integrate effort log | Recorder |  |  |  |  | x
|  | 11. Present in class | All | [5 empty] | x
3 | Dang Huy Son | 1. Read "SMA05-Software_Metrics_Program" and GQM chart, Viking project references | [6 empty] | x | x
Scheduled W#3
Course | SMA |  |  | Starting Date: |  | 2012-02-27
|  |  |  | 2012-02-20 | 2012-02-21 | 2012-02-22 | 2012-02-23 | 2012-02-24 | 2012-02-25 | 2012-02-26
Assignment # | Sub-Leader | Task name | Assign to | 2012-02-27 | 2012-02-28 | 2012-02-29 | 2012-03-01 | 2012-03-02 | 2012-03-03 | 2012-03-04
3 | Dang Huy Son | 2. Meeting 1 | All | x
|  | 3. Do teamworks | All | x | x | x
|  | 4. Meeting 2 | All |  |  | x
|  | 5. Make presentation file | Member |  |  | x
|  | 6. Integrate effort log | Recorder |  |  |  |  | x
|  | 7. Present in class | All | [5 empty] | x
4 | Do Minh Tam | 1. Read "SMA06-Process_and_Methodology" and GQM chart references | All | [5 empty] | x | x
Scheduled W#4
Course | SMA |  |  | Starting Date: |  | 2012-03-05
|  |  |  | 2012-02-20 | 2012-02-21 | 2012-02-22 | 2012-02-23 | 2012-02-24 | 2012-02-25 | 2012-02-26
Assignment # | Sub-Leader | Task name | Assign to | 2012-03-05 | 2012-03-06 | 2012-03-07 | 2012-03-08 | 2012-03-09 | 2012-03-10 | 2012-03-11
4 | Do Minh Tam | 2. Meeting 1 | All | x
|  | 3. Do teamworks | All | x | x | x
|  | 4. Meeting 2 | All |  |  | x
|  | 5. Make presentation file | Member |  |  | x
|  | 6. Integrate effort log | Recorder |  |  |  |  | x
|  | 7. Present in class | All | [5 empty] | x
5 | Nguyen Trung Tin | 1. Read "SMA07-Schedule" and network diagram, wbs references | All | [5 empty] | x | x
Scheduled W#5
Course | SMA |  |  | Starting Date: |  | 2012-03-12
|  |  |  | 2012-02-20 | 2012-02-21 | 2012-02-22 | 2012-02-23 | 2012-02-24 | 2012-02-25 | 2012-02-26
Assignment # | Sub-Leader | Task name | Assign to | 2012-03-12 | 2012-03-13 | 2012-03-14 | 2012-03-15 | 2012-03-16 | 2012-03-17 | 2012-03-18
5 | Nguyen Trung Tin | 2. Meeting 1 | All | x
|  | 3. Do teamworks | All | x | x | x
|  | 4. Meeting 2 | All |  |  | x
|  | 5. Make presentation file | Member |  |  | x
|  | 6. Integrate effort log | Recorder |  |  |  |  | x
|  | 7. Present in class | All | [5 empty] | x
6 | Le Dinh Thach Huyen | 1. Read "SMA08-Productivity" and effort log data collected references | All | [5 empty] | x | x
Scheduled W#6
Course | SMA |  |  | Starting Date: |  | 2012-03-19
|  |  |  | 2012-02-20 | 2012-02-21 | 2012-02-22 | 2012-02-23 | 2012-02-24 | 2012-02-25 | 2012-02-26
Assignment # | Sub-Leader | Task name | Assign to | 2012-03-19 | 2012-03-20 | 2012-03-21 | 2012-03-22 | 2012-03-23 | 2012-03-24 | 2012-03-25
6 | Le Dinh Thach Huyen | 2. Meeting 1 | All | x
|  | 3. Do teamworks | All | x | x | x
|  | 4. Meeting 2 | All |  |  | x
|  | 5. Make presentation file | Member |  |  | x
|  | 6. Integrate effort log | Recorder |  |  |  |  | x
|  | 7. Present in class | All | [5 empty] | x
7 | Dang Huy Son | 1. Read "SMA09-Budget" and NPV, ROI, Payback Period and Breakeven Analysis, VP Marketing Viking Business Estimates references | All | [5 empty] | x | x
Scheduled W#7
Course | SMA |  |  | Starting Date: |  | 2012-03-26
|  |  |  | 2012-02-20 | 2012-02-21 | 2012-02-22 | 2012-02-23 | 2012-02-24 | 2012-02-25 | 2012-02-26
Assignment # | Sub-Leader | Task name | Assign to | 2012-03-26 | 2012-03-27 | 2012-03-28 | 2012-03-29 | 2012-03-30 | 2012-03-31 | 2012-04-01
7 | Dang Huy Son | 2. Meeting 1 | All | x
|  | 3. Do teamworks | All | x | x | x
|  | 4. Meeting 2 | All |  |  | x
|  | 5. Make presentation file | Member |  |  | x
|  | 6. Integrate effort log | Recorder |  |  |  |  | x
|  | 7. Present in class | All | [5 empty] | x
8 | Do Minh Tam | 1. Read "SMA10-Earned_Value" references | All | [5 empty] | x | x
Scheduled W#8
Course | SMA |  |  | Starting Date: |  | 2012-04-02
|  |  |  | 2012-02-20 | 2012-02-21 | 2012-02-22 | 2012-02-23 | 2012-02-24 | 2012-02-25 | 2012-02-26
Assignment # | Sub-Leader | Task name | Assign to | 2012-04-02 | 2012-04-03 | 2012-04-04 | 2012-04-05 | 2012-04-06 | 2012-04-07 | 2012-04-08
8 | Do Minh Tam | 2. Meeting 1 | All | x
|  | 3. Do teamworks | All | x | x | x
|  | 4. Meeting 2 | All |  |  | x
|  | 5. Make presentation file | Member |  |  | x
|  | 6. Integrate effort log | Recorder |  |  |  |  | x
|  | 7. Present in class | All | [5 empty] | x
9 | Nguyen Trung Tin | 1. Read "SMA11-Quality" references | All | [5 empty] | x | x
Scheduled W#9
Course | SMA |  |  | Starting Date: |  | 2012-04-09
|  |  |  | 2012-02-20 | 2012-02-21 | 2012-02-22 | 2012-02-23 | 2012-02-24 | 2012-02-25 | 2012-02-26
Assignment # | Sub-Leader | Task name | Assign to | 2012-04-09 | 2012-04-10 | 2012-04-11 | 2012-04-12 | 2012-04-13 | 2012-04-14 | 2012-04-15
9 | Nguyen Trung Tin | 2. Meeting 1 | All | x
|  | 3. Do teamworks | All | x | x | x
|  | 4. Meeting 2 | All |  |  | x
|  | 5. Make presentation file | Member |  |  | x
|  | 6. Integrate effort log | Recorder |  |  |  |  | x
|  | 7. Present in class | All | [5 empty] | x
10 | Le Dinh Thach Huyen | 1. Read "SMA12-Risk_Management" references | All | [5 empty] | x | x
Scheduled W#10
Course | SMA |  |  | Starting Date: |  | 2012-04-16
|  |  |  | 2012-02-20 | 2012-02-21 | 2012-02-22 | 2012-02-23 | 2012-02-24 | 2012-02-25 | 2012-02-26
Assignment # | Sub-Leader | Task name | Assign to | 2012-04-16 | 2012-04-17 | 2012-04-18 | 2012-04-19 | 2012-04-20 | 2012-04-21 | 2012-04-22
10 | Le Dinh Thach Huyen | 2. Meeting 1 | All | x
|  | 3. Do teamworks | All | x | x | x
|  | 4. Meeting 2 | All |  |  | x
|  | 5. Make presentation file | Member |  |  | x
|  | 6. Integrate effort log | Recorder |  |  |  |  | x
|  | 7. Present in class | All | [5 empty] | x
11 | Dang Huy Son | 1. Read "SMA14-Customer_Sactisfaction" references | All | [5 empty] | x | x
Scheduled W#11
Course | SMA |  |  | Starting Date: |  | 2012-04-23
|  |  |  | 2012-02-20 | 2012-02-21 | 2012-02-22 | 2012-02-23 | 2012-02-24 | 2012-02-25 | 2012-02-26
Assignment # | Sub-Leader | Task name | Assign to | 2012-04-23 | 2012-04-24 | 2012-04-25 | 2012-04-26 | 2012-04-27 | 2012-04-28 | 2012-04-29
11 | Dang Huy Son | 2. Meeting 1 | All | x
|  | 3. Do teamworks | All | x | x | x
|  | 4. Meeting 2 | All |  |  | x
|  | 5. Make presentation file | Member |  |  | x
|  | 6. Integrate effort log | Recorder |  |  |  |  | x
|  | 7. Present in class | All | [5 empty] | x
12 | Do Minh Tam | 1. Read "SMA15-Team_Morale" references | All | [5 empty] | x | x
Scheduled W#12
Course | SMA |  |  | Starting Date: |  | 2012-04-30
|  |  |  | 2012-02-20 | 2012-02-21 | 2012-02-22 | 2012-02-23 | 2012-02-24 | 2012-02-25 | 2012-02-26
Assignment # | Sub-Leader | Task name | Assign to | 2012-04-30 | 2012-05-01 | 2012-05-02 | 2012-05-03 | 2012-05-04 | 2012-05-05 | 2012-05-06
12 | Do Minh Tam | 2. Meeting 1 | All | x
|  | 3. Do teamworks | All | x | x | x
|  | 4. Meeting 2 | All |  |  | x
|  | 5. Make presentation file | Member |  |  | x
|  | 6. Integrate effort log | Recorder |  |  |  |  | x
|  | 7. Present in class | All | [5 empty] | x
13 | Nguyen Trung Tin | 1. Read "SMA16-Estimation_and_Historycal_Data" references | All | [5 empty] | x | x
Scheduled W#13
Course | SMA |  |  | Starting Date: |  | 2012-05-07
|  |  |  | 2012-02-20 | 2012-02-21 | 2012-02-22 | 2012-02-23 | 2012-02-24 | 2012-02-25 | 2012-02-26
Assignment # | Sub-Leader | Task name | Assign to | 2012-05-07 | 2012-05-08 | 2012-05-09 | 2012-05-10 | 2012-05-11 | 2012-05-12 | 2012-05-13
13 | Nguyen Trung Tin | 2. Meeting 1 | All | x
|  | 3. Do teamworks | All | x | x | x
|  | 4. Meeting 2 | All |  |  | x
|  | 5. Make presentation file | Member |  |  | x
|  | 6. Integrate effort log | Recorder |  |  |  |  | x
|  | 7. Present in class | All | [5 empty] | x
14 | Le Dinh Thach Huyen | 1. Read "SMA17-Communicating_with_Stakeholders" references | All | [5 empty] | x | x
Scheduled W#14
Course | SMA |  |  | Starting Date: |  | 2012-05-14
|  |  |  | 2012-02-20 | 2012-02-21 | 2012-02-22 | 2012-02-23 | 2012-02-24 | 2012-02-25 | 2012-02-26
Assignment # | Sub-Leader | Task name | Assign to | 2012-05-14 | 2012-05-15 | 2012-05-16 | 2012-05-17 | 2012-05-18 | 2012-05-19 | 2012-05-20
14 | Le Dinh Thach Huyen | 2. Meeting 1 | All | x
|  | 3. Do teamworks | All | x | x | x
|  | 4. Meeting 2 | All |  |  | x
|  | 5. Make presentation file | Member |  |  | x
|  | 6. Integrate effort log | Recorder |  |  |  |  | x
|  | 7. Present in class | All | [5 empty] | x
15 | Dang Huy Son | 1. Read "SMA18-Experimenting_and_Pittfalls" references | All | [5 empty] | x | x
Scheduled W#15
Course | SMA |  |  | Starting Date: |  | 2012-05-21
|  |  |  | 2012-02-20 | 2012-02-21 | 2012-02-22 | 2012-02-23 | 2012-02-24 | 2012-02-25 | 2012-02-26
Assignment # | Sub-Leader | Task name | Assign to | 2012-05-21 | 2012-05-22 | 2012-05-23 | 2012-05-24 | 2012-05-25 | 2012-05-26 | 2012-05-27
15 | Dang Huy Son | 2. Meeting 1 | All | x
|  | 3. Do teamworks | All | x | x | x
|  | 4. Meeting 2 | All |  |  | x
|  | 5. Make presentation file | Member |  |  | x
|  | 6. Integrate effort log | Recorder |  |  |  |  | x
|  | 7. Present in class | All | [5 empty] | x