## Top Viking's risks
ID | Risk and Description | Type of risk | Probability | Impact | Priority | Recommendation
1 | Customer don’t know what their needs ,set out thinks is ambigous | Requirement risk | Likely | High | 5 | Requirement engineer should fine clearly information this project before meet customer and try collect customer need. You can use method as brain storming, prototype,etc…
2 | Estimate plan don't exactly | Schedule risk | Certainly | Very High | 2 | Training add about skills make plan
3 | Lack management risks and change | Plan risk | Certainly | Very High | 3 | Must always monitor and control project for make decisions ontime.
4 | Estimate budget not exactly | Budget risk | Possible | Medium | 6 | Need estimate carfully more than
5 | Estimate human resource not enough | Resource risk | Likely | Low | 12 | You should have resources backup for your project
6 | Collect not enough requirements and don't meet customer when need | Develop risk | Certainly | Very High | 4 | Improve teamwork in project and communication with customer
7 | Task does not define clearly, lack of necessary work task, unreasonable allocation in each period | Schedule risk | Certainly | Very High | 1 | Use WBS to indentify task for project Celebrate the meeting of senior to indentify task. Usually update plan
8 | Developer not skill for develop project and must retraining | Resource risk | Possible | Medium | 11 | Prepare full skills for impliment project
9 | PM not monitor and control progress | Resource risk | Likely | Low | 13 | This is mistake of PM, we need make method prevent
10 | Architect design not exactly | Develop risk | Possible | High | 7 | Must analysis clearly all requiments and review period design
11 | Lack equipment for develop project | Resource risk | Likely | Medium | 9 | You must define resource before implement project
12 | Enviroment effect performance of personel( Ex: conflict between some member) | People risk | Likely | Medium | 14 | Create enviroment communication for team member of project
13 | The scope of the project is not clearly outlined | Scope risk | Possible | High | 8 | Define clearly outlined with customer
14 | Maket exchange when product deliverables | Vision risk | Likely | Medium | 10 | Have vision far about trend future