## Equipment
Equipment | Quantity | Cost | Total | Note
Computer | 5 | 300 | 1500
Router | 1 | 100 | 100
Printer | 1 | 200 | 200
Server | 1 | 1000 | 1000
Windows xp license | 5 | 250 | 1250
Windows server 2003 license with 5 User CALs | 1 | 149 | 149
Office 2003 professional license | 5 | 490 | 2450 | Include Word, Excel, Visio, Powerpoint and MS project
WBS chart pro license | 5 | 50 | 250
|  | Total | 6899

## Salary
Task Name | Duration | Start | Finish | Resource Names | Cost
Viking project | 225 days | Thu 3/15/12 | Wed 1/23/13 |  | 15552
Planning | 6 days | Fri 3/16/12 | Fri 3/23/12 |  | 224
Estimate | 4 days | Fri 3/16/12 | Wed 3/21/12 |  | 128
Collect data | 2 days | Fri 3/16/12 | Mon 3/19/12 | Tin | 64
Mesurement and metrics | 2 days | Tue 3/20/12 | Wed 3/21/12 | Son | 64
Schedule | 2 days | Thu 3/22/12 | Fri 3/23/12 | Son | 64
Analysis goals and object | 1 day | Fri 3/16/12 | Fri 3/16/12 |  | 32
Define goals and object | 1 day | Fri 3/16/12 | Fri 3/16/12 | Van | 32
Kick off | 11 days | Mon 3/26/12 | Mon 4/9/12 |  | 544
Define project team | 1 day | Mon 3/26/12 | Mon 3/26/12 |  | 32
Define resource | 1 day | Mon 3/26/12 | Mon 3/26/12 | Van | 32
Define team policy | 1 day | Mon 3/26/12 | Mon 3/26/12 | Tam | 0
Team role, responsibility | 1 day | Mon 3/26/12 | Mon 3/26/12 | Tam | 0
Review plan | 3 days | Tue 3/27/12 | Thu 3/29/12 | Van | 96
Review process | 3 days | Thu 3/29/12 | Mon 4/2/12 | Van | 96
Discuss risks and changes | 5 days | Tue 4/3/12 | Mon 4/9/12 |  | 320
Define risk and change management process | 2 days | Tue 4/3/12 | Wed 4/4/12 | Son,Tam | 128
Change management plan | 3 days | Thu 4/5/12 | Mon 4/9/12 | Son | 96
Risk management plan | 3 days | Thu 4/5/12 | Mon 4/9/12 | Tam | 96
Requirement | 13 days | Mon 4/9/12 | Wed 4/25/12 |  | 416
Get requirement | 3 days | Mon 4/9/12 | Wed 4/11/12 | Tam,Son | 96
Analysis requirement | 10 days | Thu 4/12/12 | Wed 4/25/12 |  | 320
Make SRS | 5 days | Thu 4/12/12 | Wed 4/18/12 | Tam | 160
Make URD | 5 days | Thu 4/19/12 | Wed 4/25/12 | Son | 160
Architect and design | 40 days | Thu 4/26/12 | Wed 6/20/12 |  | 1280
Architect and design | 40 days | Thu 4/26/12 | Wed 6/20/12 |  | 544
System architect document | 3 days | Tue 5/29/12 | Thu 5/31/12 | Son | 96
High level design | 3 days | Fri 6/1/12 | Tue 6/5/12 | Tam | 96
Detailed design | 11 days | Wed 6/6/12 | Wed 6/20/12 | Tam | 352
Analysis system architect | 23 days | Thu 4/26/12 | Mon 5/28/12 |  | 736
Define architect the drivers | 15 days | Thu 4/26/12 | Wed 5/16/12 | Son | 480
Define achitect structures | 8 days | Thu 5/17/12 | Mon 5/28/12 | Son | 256
Implement | 135 days | Thu 6/21/12 | Wed 12/26/12 |  | 4480
Coding | 90 days | Thu 6/21/12 | Wed 10/24/12 | Son,Tam,Tin | 2880
Fix bug | 30 days | Thu 11/15/12 | Wed 12/26/12 | Son,Tam,Tin | 1440
Integrated | 5 days | Thu 10/25/12 | Wed 10/31/12 | Son | 160
Testing | 105 days | Thu 6/21/12 | Wed 11/14/12 |  | 608
Test plan | 3 days | Thu 6/21/12 | Mon 6/25/12 | Van,Tam | 192
System test | 2 days | Tue 11/13/12 | Wed 11/14/12 | Tam | 64
Unit test | 32 days | Tue 9/25/12 | Wed 11/7/12 |  | 256
Test case | 1 day | Thu 11/1/12 | Thu 11/1/12 | Son,Tam,Tin | 64
Unit test script | 2 days | Fri 11/2/12 | Mon 11/5/12 | Son,Tam,Tin | 128
Implement test | 2 days | Tue 11/6/12 | Wed 11/7/12 | Tin | 64
Integrated test | 3 days | Thu 11/8/12 | Mon 11/12/12 | Tam | 96
Deployment | 17 days | Sat 12/29/12 | Mon 1/21/13 |  | 896
Release and install | 2 days | Sat 12/29/12 | Mon 12/31/12 | Huyen | 64
Collect feedback | 7 days | Tue 1/1/13 | Wed 1/9/13 | Huyen | 224
Analysis feedback | 3 days | Thu 1/10/13 | Mon 1/14/13 | Huyen,Son,Tam,Van,Tin | 288
Acceptance test | 5 days | Tue 1/15/13 | Mon 1/21/13 | Tam,Van | 320
Close out | 20 days | Thu 12/27/12 | Wed 1/23/13 |  | 160
Lesson learned | 1 day | Tue 1/22/13 | Tue 1/22/13 | Van | 32
Make close out document | 20 days | Thu 12/27/12 | Wed 1/23/13 |  | 128
User manual | 2 days | Thu 12/27/12 | Fri 12/28/12 | Huyen | 64
Close sure project plan | 2 days | Tue 1/22/13 | Wed 1/23/13 | Van,Tam | 64
Management | 217 days | Mon 3/26/12 | Tue 1/22/13 |  | 6944
Report management | 217 days | Mon 3/26/12 | Tue 1/22/13 | Van | 0
Status report | 217 days | Mon 3/26/12 | Tue 1/22/13 | Van | 0
Weekly report | 217 days | Mon 3/26/12 | Tue 1/22/13 | Van | 0
Change mangement | 217 days | Mon 3/26/12 | Tue 1/22/13 | Van | 0
Risk control | 217 days | Mon 3/26/12 | Tue 1/22/13 | Van | 0
management |  |  |  | Van | 6944
Maintain | 12 Days |  |  |  | 384
Total salary cost | 15936

## Support
Content | Duration (month) | Fee for a month | Total cost | Note
Rent office | 13 | 2000 | 26000 | Inlude power and water
Internet fee | 13 | 200 | 2600
|  | Total | 28600

## Training
Content | Cost | Number of member join | Total
Programming | 200 | 5 | 1000
Design | 200 | 2 | 400
|  | Total | 1400 | 5000
15936
6899
28600
1400
2500
2600
62935
12587
88109