## Cost
Operating Expense
Salary | 44200
Training | 2000
Travel & Entertainment | 12100
Facilities | 27500
Total Operating Expense | 85800
Capital Expense
Equipment | 7400
Total Capital Expense | 7400
Total expense | 93200
Position Assumptions for year 1
Title | Pay per hour | Working hour | Salary | Total
PM | 10 | 2112 | 21120 | 44200
System architect | 20 | 312 | 6240
System analyst | 20 | 216 | 4320
Developers | 3 | 1000 | 3000
Tester | 5 | 144 | 720
Technical writer | 4 | 88 | 352
Functional management | 4 | 2112 | 8448
Headcount Projection | Mar Y1 | Apr Y1 | May Y1 | Jun Y1 | Jul Y1 | Aug Y1 | Sep Y1 | Oct Y1 | Nov Y1 | Dec Y1 | Jan Y2
PM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
System architect | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
System analyst | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Developers | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
Tester | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 2 | 2 | 0 | 0
Technical writer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Functional management | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Total Headcount | 2 | 3 | 4 | 11 | 8 | 8 | 10 | 10 | 10 | 9 | 3
Salary Projection | Mar Y1 | Apr Y1 | May Y1 | Jun Y1 | Jul Y1 | Aug Y1 | Sep Y1 | Oct Y1 | Nov Y1 | Dec Y1 | Jan Y2
PM | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 | 1920
System architect |  | 2720 | 3520
System analyst |  | 2080 |  | 2240
Developers |  |  |  | 2280 |  |  |  |  | 720
Tester |  |  |  | 120 | [5 empty] | 400 | 200
Technical writer | [9 empty] | 128 | 224
Functional management | 768 | 768 | 768 | 768 | 768 | 768 | 768 | 768 | 768 | 768 | 768
Total Salaries | 2688 | 7488 | 6208 | 7328 | 2688 | 2688 | 2688 | 2688 | 3408 | 3216 | 3112
Equipment Projection | Mar Y1
PM | 600
System architect | 400
System analyst | 400
Developers | 4200
Tester | 1200
Technical writer | 300
Functional management | 300
Total | 7400
Support Projection | Mar Y1 | Apr Y1 | May Y1 | Jun Y1 | Jul Y1 | Aug Y1 | Sep Y1 | Oct Y1 | Nov Y1 | Dec Y1 | Jan Y2
Rent office | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300
Internet | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200
Total | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500
Training Projection | Mar Y1
Developers | 1200
Tester | 600
Technical writer | 200
Total | 2000
Travel Projection | Mar Y1 | Apr Y1 | May Y1 | Jun Y1 | Jul Y1 | Aug Y1 | Sep Y1 | Oct Y1 | Nov Y1 | Dec Y1 | Jan Y2
Picnic | 500 |  | 500 |  | 500 |  | 500 |  | 500 |  | 500
Travel |  |  |  |  | 4000 | [5 empty] | 4000
Entertaiment | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Total | 600 | 100 | 600 | 100 | 4600 | 100 | 600 | 100 | 600 | 100 | 4600

## Schedule
Task Name | Duration | Start | Finish | Resource Names
Viking project | 225 days | Thu 3/15/12 | Wed 1/23/13
Planning | 6 days | Fri 3/16/12 | Fri 3/23/12
Estimate | 4 days | Fri 3/16/12 | Wed 3/21/12
Collect data | 2 days | Fri 3/16/12 | Mon 3/19/12 | PM
Mesurement and metrics | 2 days | Tue 3/20/12 | Wed 3/21/12 | PM
Schedule | 2 days | Thu 3/22/12 | Fri 3/23/12 | PM
Analysis goals and object | 1 day | Fri 3/16/12 | Fri 3/16/12
Define goals and object | 1 day | Fri 3/16/12 | Fri 3/16/12 | PM
Kick off | 11 days | Mon 3/26/12 | Mon 4/9/12
Define project team | 1 day | Mon 3/26/12 | Mon 3/26/12
Define resource | 1 day | Mon 3/26/12 | Mon 3/26/12 | PM
Define team policy | 1 day | Mon 3/26/12 | Mon 3/26/12 | PM
Team role, responsibility | 1 day | Mon 3/26/12 | Mon 3/26/12 | PM
Review plan | 3 days | Tue 3/27/12 | Thu 3/29/12 | PM
Review process | 3 days | Thu 3/29/12 | Mon 4/2/12 | PM
Discuss risks and changes | 5 days | Tue 4/3/12 | Mon 4/9/12
Define risk and change management process | 2 days | Tue 4/3/12 | Wed 4/4/12 | PM
Change management plan | 3 days | Thu 4/5/12 | Mon 4/9/12 | PM
Risk management plan | 3 days | Thu 4/5/12 | Mon 4/9/12 | PM
Requirement | 13 days | Mon 4/9/12 | Wed 4/25/12
Get requirement | 3 days | Mon 4/9/12 | Wed 4/11/12 | System architect, system design
Analysis requirement | 10 days | Thu 4/12/12 | Wed 4/25/12
Make SRS | 5 days | Thu 4/12/12 | Wed 4/18/12 | System architect, system design
Make URD | 5 days | Thu 4/19/12 | Wed 4/25/12 | System architect, system design
Architect and design | 40 days | Thu 4/26/12 | Wed 6/20/12
Architect and design | 40 days | Thu 4/26/12 | Wed 6/20/12
System architect document | 3 days | Tue 5/29/12 | Thu 5/31/12 | System architect
High level design | 3 days | Fri 6/1/12 | Tue 6/5/12 | System design
Detailed design | 11 days | Wed 6/6/12 | Wed 6/20/12 | System design
Analysis system architect | 23 days | Thu 4/26/12 | Mon 5/28/12
Define architect the drivers | 15 days | Thu 4/26/12 | Wed 5/16/12 | System architect
Define achitect structures | 8 days | Thu 5/17/12 | Mon 5/28/12 | System architect
Implement | 135 days | Thu 6/21/12 | Wed 12/26/12
Coding | 90 days | Thu 6/21/12 | Wed 10/24/12 | Developer
Fix bug | 30 days | Thu 11/15/12 | Wed 12/26/12 | Developer
Integrated | 5 days | Thu 10/25/12 | Wed 10/31/12 | Developer
Testing | 105 days | Thu 6/21/12 | Wed 11/14/12
Test plan | 3 days | Thu 6/21/12 | Mon 6/25/12 | Tester
System test | 2 days | Tue 11/13/12 | Wed 11/14/12 | Tester
Unit test | 32 days | Tue 9/25/12 | Wed 11/7/12
Test case | 1 day | Thu 11/1/12 | Thu 11/1/12 | Tester
Unit test script | 2 days | Fri 11/2/12 | Mon 11/5/12 | Tester
Implement test | 2 days | Tue 11/6/12 | Wed 11/7/12 | Tester
Integrated test | 3 days | Thu 11/8/12 | Mon 11/12/12 | Tester
Deployment | 17 days | Sat 12/29/12 | Mon 1/21/13
Release and install | 2 days | Sat 12/29/12 | Mon 12/31/12 | Technical writer
Collect feedback | 7 days | Tue 1/1/13 | Wed 1/9/13 | Technical writer
Analysis feedback | 3 days | Thu 1/10/13 | Mon 1/14/13 | PM
Acceptance test | 5 days | Tue 1/15/13 | Mon 1/21/13 | Tester
Close out | 20 days | Thu 12/27/12 | Wed 1/23/13
Lesson learned | 1 day | Tue 1/22/13 | Tue 1/22/13 | PM
Make close out document | 20 days | Thu 12/27/12 | Wed 1/23/13
User manual | 2 days | Thu 12/27/12 | Fri 12/28/12 | Technical writer
Close sure project plan | 2 days | Tue 1/22/13 | Wed 1/23/13 | PM
Management | 217 days | Mon 3/26/12 | Tue 1/22/13
Report management | 217 days | Mon 3/26/12 | Tue 1/22/13 | PM
Status report | 217 days | Mon 3/26/12 | Tue 1/22/13 | PM
Weekly report | 217 days | Mon 3/26/12 | Tue 1/22/13 | PM
Change mangement | 217 days | Mon 3/26/12 | Tue 1/22/13 | PM
Risk control | 217 days | Mon 3/26/12 | Tue 1/22/13 | PM
management |  |  |  | PM
Maintain | 12 Days
Total salary cost | #REF!