## Sheet1
RISK REGISTER
Project Name: SMS Project | [8 empty] | Version: 1.0
Project Team: K15T01_Team#1 | [8 empty] | Date:
Risk Category | ID | Risk Description | Risk owner | Likehood | Size (week) | Probability | Impact time | Impact scope | Impact quality | Priority | RE | Key priority
schedule | R001 | The Schedule doesn’t provide enough time to complete the project | PM | 60 | 0.2 | 90% | 40 | 40 | 40 |  | 0.18 | Rating | Color
| R002 | The schedule doesn’t list all the activities and task required | PM | 60 | 0.2 | 80% | 60 | 60 | 40 |  | 0.16 | Very low | White
requirement | R003 | The requirements have not been clearly specified | Requirement engineers | 80 | 1 | 50% | 80 | 80 | 80 |  | 0.5 | Low | Green
People | R004 | There is a shortage of member available when required (because missing member, …) | Team member | 40 | 2 | 95% | 40 | 40 | 20 |  | 1.9 | Medium | Yellow
| R005 | Lack in communication | PM and team | 40 | 2 | 20% | 20 | 20 | 20 |  | 0.4 | High | Orange
| R006 | Lack of developer's skill | Developers | 40 | 4 | 90% | 40 | 40 | 20 |  | 3.6 | Very High | Red
Budget | R007 | Budget cut | Customer, market or new company policy | 20 | 14 | 5% | 100 | 100 | 20 |  | 0.7
| R008 | Not enough budget, over budget. | PM | 80 | 0.1 | 80% | 40 | 60 | 20 |  | 0.08
Product | R009 | Product do not meet customer require (customer satisfaction) | PM | 80 | 5 | 20% | 40 | 60 | 40 |  | 1
| R010 | Quality of product is bad | PM | 80 | 5 | 20% | 60 | 60 | 80 |  | 1
Likelihood
Title |  | Score | Description
Very Low |  | 20 | The risk is highly unlikely and will be recorded but not monitored
Low |  | 40 | The risk is unlikely but will be monitored throughout the project
Medium |  | 60 | The risk likely as it is clear that the risk may occur
High |  | 80 | The risk very likely, based on the circumstances of the project
Very high |  | 100 | The risk is high likely, as the circumstances that will cause this risk to occur are also very likely to occur
Impact time
Title |  | Score | Description
Very Low |  | 20 | The risk will have an insignificant impact on the project
Low |  | 40 | The risk will have a minor impact on the project (< 5% deviation schedule end – date)
Medium |  | 60 | The risk will have a minor impact on the project (5 - <10% deviation schedule end – date)
High |  | 80 | The risk will have a minor impact on the project (10 - 25% deviation schedule end – date)
Very high |  | 100 | The risk will have a minor impact on the project (> 25% deviation schedule end – date)
Impact scope
Title |  | Score | Description
Very Low |  | 20 | The risk will have an insignificant impact on the project
Low |  | 40 | The risk will have a minor impact on the project (< 5% deviation scope)
Medium |  | 60 | The risk will have a minor impact on the project (5 - <10% deviation scope)
High |  | 80 | The risk will have a minor impact on the project (10 - 25% deviation scope)
Very high |  | 100 | The risk will have a minor impact on the project (> 25% deviation scope)
Impact quality
Title |  | Score | Description
Very Low |  | 20 | Quality of product be less affected
Low |  | 40 | Product operation is normal, error rate is 10 on 100 KLOC
Medium |  | 60 | Product operation is normal, error rate is >10 and <100 on 100 KLOC
High |  | 80 | Product operation is unsable error rate is >100 on 100 KLOC
Very high |  | 100 | Product can not operate