## SEP
Time Recording Log For: SEP Project
SUMMARY: TIME FOR DOING PROJECT
Name: | Do Minh Tam |  |  | Date: |  | 2012-05-21
[10 empty] | WORKS/ARTIFACTS | HOURS
Week | Date | Start | Stop | Delta Time | Phase | Activity | Artifact | C | U | Requirement
1 | 2012-05-21 | 10:30 | 12:20 | 2 | Re | Team Meeting |  |  |  | Ananlysis & Design
|  | 12:20 | 12:30 | 0.25 | Report | Team Meeting Report |  |  |  | Development
|  | 15:00 | 15:30 | 0.5 | Re | Định hình yêu cầu | Định hình sơ bộ yêu cầu - ver0.1 |  |  | Testing
| 2012-05-22 | 11:00 | 14:10 | 0.5 | Re | Team Meeting |  |  |  | Packaging & Deployment
|  | 14:10 | 14:20 | 0.25 | Report | Team Meeting Report |  |  |  | Planning + PM
|  | 14:20 | 14:50 | 0.5 | Re | Initial Requirement | Định hình sơ bộ yêu cầu - ver0.2 |  |  | CM
| 2012-05-25 | 12:10 | 13:10 | 1 | Re | Initial Requirement | Định hình sơ bộ yêu cầu - ver0.3 |  |  | Report
|  | 14:10 | 14:14 | 0 | Re | Initial Requirement | Định hình sơ bộ yêu cầu - ver0.4 |  |  | TOTAL
|  | 14:45 | 15:15 | 0.5 | Re | Team Meeting |  |  |  | ON AVERAGE (hours/week)
|  | 16:10 | 17:20 | 1 | Re | Cus Meeting
|  | 22:35 | 23:05 | 0.5 | Report | Team, Customer Meeting Report
| 2012-05-27 | 14:30 | 3:00 | 0.5 | Report | Team Meeting Report
|  | 10:20 | 12:35 | 2 | Re | Team Meeting
2 | 2012-05-28 | 0:00 AM | 2:30 | 2.5 | Re | Analysize requirement
|  | 9:40 | 11:05 | 1.5 | Re | Mentor Meeting
|  | 16:00 | 16:15 | 0.25 | Report | Mentor Meeting Report
| 2012-05-29 | 9:30 | 11:00 | 1.5 | Re | Team Meeting
| 2012-05-30 | 6:15 | 6:19 | 0 | Report | Team Meeting Report
|  | 13:55 | 14:45 | 1 | Re | Initial Requirement | Định hình sơ bộ yêu cầu - ver0.5
| 2012-05-31 | 9:45 | 11:15 | 1.5 | Re | Team Meeting
|  | 13:00 | 13:05 | 0 | Report | Team Meeting Report
| 2012-06-02 | 9:30 | 10:00 | 0.5 | Re | Team Meeting
|  | 10:00 | 11:00 | 1 | Re | Customer Meeting
|  | 12:40 | 3:10 | 2.5 | Re | Team Meeting
|  | 16:35 | 4:50 | 0.25 | Report | Team, Customer Meeting Report
|  | 21:15 | 23:59 | 2.75 | Re | Analysize requirement
| 2012-06-03 | 21:30 | 22:30 | 1 | Re | Analysize requirement
3
4
5
6
7
8
9
10
11

## SAD
Time Recording Log For: SAD Final Project
SUMMARY: TIME FOR DOING PROJECT
Name: | Do Minh Tam |  |  | Date: |  | 2012-05-21
[10 empty] | WORKS/ARTIFACTS | HOURS
Week | Date | Start | Stop | Delta Time | Phase | Activity | Artifact | C | U | Requirement & Analysis
| 2012-05-23 | 9:50 | 12:15 | 2.5 | Re | Team Meeting |  |  |  | Architecture Design
|  | 12:15 | 12:25 | 0.25 | Report | Team Meeting Report |  |  |  | Implement
|  | 13:30 | 14:20 | 1 | Re | Use Case Diagram | Use Case Diagram - v0.1 |  |  | System Test
1 |  | 14:20 | 15:25 | 1 | Re | URD template | URD |  |  | Deployment & Maintenance
| 2012-05-24 | 19:30 | 23:59 | 5.5 | Re | Analysize requirement |  |  |  | Report
| 2012-05-25 | 0:00 AM | 4:00 | 4 | Re | Analysize requirement |  |  |  | TOTAL
ON AVERAGE (hours/week)
| 2012-05-28 | 16:15 | 18:45 | 2.5 | Re | Analysize requirement
|  | 17:30 | 23:15 | 5.75 | Re | Analysize requirement
2 |  | 22:15 | 23:36 | 1.25 | Re | Review UC Description of Tin Nguyen | UC Description - v0.1
| 2012-05-30 | 9:30 | 11:15 | 1.75 | Re | Team Meeting
|  | 13:10 | 13:15 | 0 | Report | Team Meeting Report
|  | 13:40 | 13:55 | 0.25 | Re | UC Diagram | Use Case Diagram - v0.2
| 2012-06-01 | 9:30 | 11:00 | 1.5 | Re | References DreamWeaver, ASP .Net, WebMatrix
| 2012-06-03 | 0:00 AM | 3:30 | 3.5 | Re | References ASP.Net & WebMatrix
|  | 15:15 | 19:15 | 4 | Re | References ASP.Net & WebMatrix
| 2012-06-04 | 4:45 | 8:40 | 4 | Re | Analysize requirement
3
4
5
6
7
8
9
10
11

## Other
Time Recording Log For: Others Project
SUMMARY: TIME FOR DOING PROJECT
Name: | Do Minh Tam |  |  | Date: |  | 2012-05-21
[10 empty] | WORKS/ARTIFACTS | HOURS
Week | Date | Start | Stop | Delta Time | Type | Activity | Artifact | C | U
1
TOTAL
ON AVERAGE (hours/week)
2
3
4
5
6
7
8
9
10
11