## Sheet1
0 | measure | why we measure | data collection | source | metrics | description
1 | Progress | provide status of project | task on wbs task completed | schedule WBS project tracking spreadsheet | 1. % task completed = task completed / task on wbs 2. % task completed on time = task completed on time / task completed | 1. help manager follow the progress of project. Control and monitor activities in develop team. 2. help manager make decision, prepare new plans.
2 | Cost | provide information about status of using funds | ACWP (actual cost of work performed) | actual cost spreadsheet | 1. cost variance = BCWP-ACWP 2. schedule variance (SV) = BCWP - BCWS | 1. help manager control cost of project. The difference between BCWP and ACWP gives manager his/her cost variance. 2. if CV = 0, project is on budget 3. if SV = 0, project is right on schedule.
|  |  | BCWP (budget cost work performed) | project Tracking Spreadsheet
|  |  | BCWS (budget cost work schedule) | project Tracking Spreadsheet
3 | Customer satisfaction | provide information about customer statisfaction. | number of defect reported | delivery report | 1. rate % of fixed defect reported = number of fixed defect reported / number of defect reported 2. rate % of function completed 3. rate % function satisfic customer. | 1. help manager know level of customer satisfaction when we meet their requirements. 2. help manager control requirement change,
number of defect reported fixed
|  |  | number of function in requirement | SRS - SDS
|  |  | number of complete function | develop report
|  |  | number of function that customer think it is okay | delivery report
4 | Defect | provide information about quality of source code | number of code line | source code review report | 1. rate defect / one thousand of code lines 2. % fixed defect / number of defect 3. average time to fix a defect | 1. help manager know quality of source line 2. know perfomance of fixing defect.
number of defect
number of fixed defect
total time to fix defect