## Sheet1
No.	Measure	Why we measure	Source	Data Collection	Metric	Description for Metric
1	Progress	1. Provide the status of project / 2. Đo % công việc hoàn thành / 3. Đo % công việc hoàn thành đúng tiến độ	1. Schedule / 2. Project tracking spreadsheet	1. Tasks on WBS / 2. Tasks completed on time (TCOT) / 3. Tasks completed (TC)	1. % công việc hoàn thành = TC/WBS / 2. % công việc hoàn thành đúng tiến độ = TCOT/TC	Nắm khối lượng công việc, đưa ra quyết định, điều chỉnh schedule cho hợp lý, …
2	Cost		1.Project tracking spreadsheet	1. BCWP (is the planned cost to complete the work that has been done) / 2. ACWP (is the cost incurred to accomplish the work that has been done to date)	1.CPI (cost performance index): / CPI = BCWP /ACWP / 2.CV (cost variance): / CV = BCWP – ACWP	1. CV (cost variance) is the difference between the planned cost for work complete and the actual cost. / 2. CPI (Cost performance index) is how much it really costs to earn the report value. / + If CPI = 1.0, we have perfect performance. / + If CPI > 1.0, we have exceptional performance. / + If CPI < 1.0, we have poor performance.
3	Quality				1. Number of completed vs. planed function points / 2. Number of passed vs. total test case (how many percents) / 3. Number of fixed vs. found defect (how many percents)	1. Base on number of functional requirements in Viking URD (table 2 page 12) and number of completed functional requirements / 2. You can know efficiency of your project and satisfaction of customer / 3. Base on actual figure when Viking project starts.
4	Process			1. Number of WBS’s tasks planned to be completed / 2. Number of WBS’s tasks completed on time / 3. Number of WBS’s tasks completed late / 4. Number of WBS’s tasks completed overdue	1. SV (Schedule variance): / SV = BCWP- BCWS / 2. SPI (Schedule Performance Index): SPI = (BCWP/BCWS)	1. SPI (schedule performance index) is how much of the original scheduled work has been accomplished. / 2. SV (schedule variance) is the difference between the planned and earned value. / + If SPI = 1.0, the project is on plan. / + If SPI > 1.0, the project is overachieving. / + If SPI < 1.0, the project is underachieving.
5	Defect			1. Number of defect / 2. Number of opened defect / 3. Number of closed defect / 4. Number Line of Code (LOC) / 5. Total time to be fixed defects	1.Defect density = Number of defect/all KLOC / 2.Average % Fixed defect = (Number of closed defect/ Number of defect) / 3. Average time to fix a defect =( Total time to be fixed defects/ Number of closed defect)	1. To help we know source code are good or bad based on standard, you can predict you must fix more or less / 2. To help you set up plan to fix defect, it get less time than you do not know average time to fix a defect
6	Customer satification			1. Delivery Schedule Rating / 2. Price Rating / 3. Cooperation Rating	1. DR = (actual days taken for delivery – accepted days for delivery) / accepted days for delivery / 2. PR = (actual amount billed – amount on the purchase order) / amount on the purchase order / 3. CR = (number of change requests received – number of change requests implemented without affecting delivery date or price) / number of change requests received	1.To accesses level of requirements stability / 2. To helps for us to understand what function stratifies customer / 3. Defines high – priority of defect that helping for decision of project manager know what defect will be fixed early
					SV (Schedule variance) / SV = BCWP- BCWS / (Schedule Performance Index) SPI = (BCWP/BCWS)