## Individual Estimate
Name: | HienNguyen | Date : | Units : Days
ID | Task Name | Estimated | Assumption
1 | Interview with customer | 1
2 | Software requirement specification | 8 | 9/12 uses case have been discovered
3 | Develop project plan | 11
4 | Deploy infrastructure | 9 | Starts from the beginning
5 | High level design | 5 | 9/12 uses case have been discovered
6 | Discover the rest of use cases | 5
7 | Detail design modules in component 1 | 10 | Component 1 includes modules such as Member, Project, User, Lifecycles, Artifacts
8 | Develop modules in component 1 | 20 | Programming language is java
9 | Test modules in component 1 | 8 | Test environment available
10 | Detail design modules in component 2 | 9 | Component 2 includes modules such as Roles, Permissions, Login, Issue
11 | Develop modules in component 2 | 13 | Programming language is java
12 | Test modules in component 2 | 9 | Test environment available
13 | Detail design modules in component 3 | 12 | Component includes modules such as Communication, Report, Syschronize data
14 | Develop modules in component 3 | 26 | Programming language is java
15 | Test modules in component 3 | 9 | Test environment unavailable
16 | Develop User-guide | 4
17 | Training | 5
18 | Perform acceptance testing | 19 | Customer is friendly
19 | Collect historical data | 8