## Individual Estimate
Name: | MungNguyen | Date : | Units : Days
ID | Task Name | Estimated | Assumption
1 | Interview with customer | 2 | 1 Requirement Engineer
2 | Software requirement specification | 6 | 9/12 uses case have been discovered, 1 Requirement Engineer
3 | Develop project plan | 5 | 1 Project Manager
4 | Deploy infrastructure | 11 | Starts from the beginning
5 | High level design | 10 | 9/12 uses case have been discovered, 1 Architect
6 | Discover the rest of use cases | 9 | 3 uses case, 1 Requiement Engineer
7 | Detail design modules in component 1 | 7 | Component 1 includes modules such as Member, Project, User, Lifecycles, Artifacts, 4 Architects
8 | Develop modules in component 1 | 20 | Programming language is java, 5 Developers
9 | Test modules in component 1 | 9 | Test environment available, 2 Tester
10 | Detail design modules in component 2 | 14 | Component 2 includes modules such as Roles, Permissions, Login, Issue; 2 Architects
11 | Develop modules in component 2 | 16 | Programming language is java, 5 Developers
12 | Test modules in component 2 | 8 | Test environment available, 2 Tester
13 | Detail design modules in component 3 | 17 | Component includes modules such as Communication, Report, Syschronize data, 1 Architect
14 | Develop modules in component 3 | 21 | Programming language is java, 1 Developers
15 | Test modules in component 3 | 9 | Test environment unavailable, 1 Tester
16 | Develop User-guide | 3 | 1 Architect
17 | Training | 7 | 2 person
18 | Perform acceptance testing | 19 | Customer is friendly, 2 Testers
19 | Collect historical data | 5 | 1 person