## DashBoard
Dashboard
| Speed |  | Performance | Testing |  | Risk
| Shedule and Cost Status |  |  |  | Defect Status
Table
| Yellow : Not good | 30
| Green : Good | 40
| Red : Warnning | 30
0
1
2
0
1
2
0
1
2
0
1
2

## Summary-Status
Summary Status
Note : | Accomplishments: Show what project team achieved, such as tasks are completed or change requests disposition completed or ABC system completed the test scripts.
Next 2 weeks tasks: Show missions plan for next 2 weeks, such as intergration test by ABC systems
Current Schedule: Show release’s milestones of project includes: Completed milestones, customer milestones and ABC systems milestones
Completed milestones Customer Milestones ABC Systems milestones
Release 1-2: Completed
Project Close-out: Milestones Customer requirement
Contract closeout: Finished ahead of schedule
Issues/Concerns: show issues of ABC system
Risks: Show risk of ABC system

## MileStone-Status
MileStone-Status
Note : Cuurent, project is belong to Transition interation. In last interation,Construction, Project lated about a hafl month
Milestone | Plan | Actual
Inception | 2010-01-01 | 2010-01-02
Elaboration | 2010-01-14 | 2010-01-18
Construction | 2010-01-27 | 2010-02-12 | Next
Transition | 2010-05-25
Close-out | 2010-06-18

## EV-Status
Note : | Performance of team development isn't well. Project can lated one week with current performance
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 12 | 13 | 14 | 15
BCWS | 364 | 596 | 931.1 | 1248 | 1564 | 1816 | 2036 | 2256 | 2451 | 2812 | 3277 | 3400 | 3800 | 4200
BCWP | 312 | 596 | 776 | 1002 | 1250 | 1489 | 1650 | 2214 | 2336 | 2484 | 2878 | 3177
ACWP | 400 | 620 | 880 | 1500 | 1700 | 1600 | 1564 | 2300 | 2245 | 2600 | 3000 | 3300
CPI | 0.78 | 0.96129 | 0.88182 | 0.668 | 0.73529 | 0.93063 | 1.055 | 0.96261 | 1.0405 | 0.95538 | 0.95933 | 0.96273
SPI | 0.85714 | 1 | 0.83342 | 0.80288 | 0.79923 | 0.81993 | 0.81041 | 0.98138 | 0.95308 | 0.88336 | 0.87824 | 0.93441
CV | -88 | -24 | -104 | -498 | -450 | -111 | 86 | -86 | 91 | -116 | -122 | -123
SV | -52 | 0 | -155.1 | -246 | -314 | -327 | -386 | -42 | -115 | -328 | -399 | -223
EAC | [11 empty] | 3300 | 3947.1199 | 4362.6062
VAC
Bull's Eyes Chart
| Note : | Project is behind schedule and above cost
Back

## Resource-Status
Resource Status Report
Table of Resource
Headcount of Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Planned | 2 | 3 | 3 | 3 | 6 | 6 | 9 | 12 | 12 | 12 | 6 | 5 | 3 | 3 | 3
Actual | 2 | 2 | 3 | 3 | 5 | 5 | 8 | 14 | 14 | 14 | 7 | 4 | 4
Note : Actual Headcount is increase in compare with Plan Headcount. But Project still lated. So, We can consider about effective team development

## Defect-Status
Defect Status
Note : | This chart show number of defect in each iteration and provide status of defect on each iteration. Beside we can compare each column with other column about number of defect different.
Current, the number of defect is too Big to control, Total of defect is about 180, but we only fix completely about 40% .
Table of Defect
| Iteration | Opened | Fixed | Closed | ReOpend
| 1 | 30 | 15 | 0 | 0
| 2 | 60 | 30 | 20 | 2
| 3 | 75 | 55 | 50 | 5
Next:

## Function-Status
Status Function Report
Note : Current , Team completed about 80% feature in compare with Total feature. This is Fun for Team developer and motivate them
Table of Number Fuction
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Total of Feature | 80 | 90 | 90 | 90 | 120 | 150 | 150 | 160 | 160 | 160 | 160 | 160 | 200
Number Feature Left | 80 | 90 | 80 | 60 | 70 | 70 | 30 | 40 | 40 | 25 | 20 | 15 | 40
Number Feature Done | 0 | 0 | 10 | 30 | 50 | 80 | 120 | 120 | 120 | 135 | 140 | 145 | 160
Next

## Testing-Status
Status Testing Report
Note : Base on data and chart,we can see that Our phase testing is cool. It same same with Lower control limmited.
Table Of Number Test Case
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Number of Test Case | 0 | 0 | 0 | 0 | 10 | 30 | 40 | 60 | 80 | 100 | 120 | 140 | 160
Number of Test Case Successful | 0 | 0 | 0 | 0 | 8 | 25 | 30 | 50 | 55 | 60 | 70 | 90 | 130
Upper Control Limit ( 99% ) | 0 | 0 | 0 | 0 | 9.9 | 29.7 | 39.6 | 59.4 | 79.2 | 99 | 118.8 | 138.6 | 158.4
Lower Control Limit ( 85% ) | 0 | 0 | 0 | 0 | 7.92 | 24.75 | 29.7 | 49.5 | 54.45 | 59.4 | 69.3 | 89.1 | 128.7
Note :
- Standard of ABC system about test case Successful is about 85% - 99 %
- So, Upper Control Limit 99%
- So, Upper Control Limit 85%
Back

## Risk-Status
Status Risk Report
Table of Risk
| Risk Level | Total
| High | 1
| Medium | 3
| Low | 0
This chart shows level of risk percent in project. Beside it provide overview about risk that help we evaluate this project on red alert
Note : | We can see percent rate of Level Risk in our project. About 100% risk belong to Medium and High Level .So this is the alert for project with current risk.
So, We have to action carefully in next interation.
Risk Report Details :
|  |  |  | Impact | Probability | Score
|  |  | Note : | Very low | Unlikely | 1
|  |  |  | Low | Possible | 2
|  |  | 1) Late Delivery : Business and revenue | Moderate | Likely | 3
|  |  | 2) Low responsiveness : Late project | High | Imminent | 4
|  |  | 3) Quality : Business and reputation loss | Very high | Certain | 5
4) Poor supplier management : Failed project
Back