## SEP
Time Recording Log For: SEP Project
SUMMARY: TIME FOR DOING PROJECT
Name: | Le Thi Bich Van |  |  | Date: |  | 2012-05-21
[10 empty] | WORKS/ARTIFACTS | HOURS
Week | Date | Start | Stop | Delta Time | Phase | Activity | Artifact | Status | U | Requirement
| 2012-05-21 | 10:30 | 12:20 | 1:50 | Requirment | Team meeting |  | Done |  | Ananlysis & Design
| 2012-05-22 | 11:00 | 14:10 | 3:10 | Requirment | Team meeting |  | Done |  | Development
| 2012-05-25 | 14:45 | 15:15 | 0:30 | Requirment | Team meeting |  | Done |  | Testing
|  | 16:10 | 17:20 | 1:10 | Requirment | Customer meeting |  | Done
| 2012-05-27 | 10:20 | 12:35 | 2:15 | Requirment | Team meeting |  | Done |  | Packaging & Deployment
| 2012-05-28 | 9:40 | 11:05 | 1:25 | Requirment | Mentor meeting |  | Done |  | Planning + PM
| 2012-05-29 | 9:30 | 11:00 | 1:30 | Requirment | Team meeting |  | Done |  | CM
| 2012-05-30 | 14:45 | 15:30 | 0:45 | Planning+PM | Reading document for: 1. How to create "Tracking Schedule" 2. Control effort of members for SEP | K15T1-Team11-MRBS-Tracking Schedule-ver0.1 | Continous |  | Report
|  | 3:52 | 6:30 | 2:38 | Planning+PM | Reading document for: 1. How to create "Tracking Schedule" 2. Control effort of members for SEP | K15T1-Team11-MRBS-Tracking Schedule-ver0.1 (Update) | Continous |  | TOTAL
| 2012-06-02 | 0:55 | 8:20 | 7:25 | Planning+PM | Create Plan & schedule | K15T1-Team11-MRBS-Schedule-ver0.1 | Continous |  | ON AVERAGE (hours/week)
|  | 9:30 | 10:00 | 0:30 | Planning+PM | Review & Discuss | K15T1-Team11-MRBS-Schedule-ver0.1 | Continous
|  | 12:40 | 15:10 | 2:30 | Planning+PM | Review & Discuss | K15T1-Team11-MRBS-Schedule-ver0.1 | Continous
| 2011-07-11 | 10:00 | 12:00 | 2:00 | Planning+PM | Baseline work | K15T1-Team11-MRBS-Schedule-ver1.1 | Continous
|  | 13:45 | 14:57 | 1:12 | Planning+PM | Baseline work | K15T1-Team11-MRBS-Schedule-ver1.2 | Done
| 2012-07-23 | 13:00 | 18:30 | 5:30 | Implement Function "loadNgayCuaTuanHienTai()" | Research "How to read barcode?" | "MRBS-v5.2" | Continous
| 2012-07-24 | 13:10 | 16:54 | 3:44 | Implement Function "loadNgayCuaTuanHienTai()" | Code Gui for Read barcode | "MRBS-v5.2" | Done
|  | 17:00 | 19:00 | 2:00 | Implement Function "loadNgayCuaTuanHienTai()" | Code gui for MainForm | "MRBS-v5.2" | Continous
| 2012-07-25 | 5:21 | 6:00 | 0:39 | Implement Function "loadNgayCuaTuanHienTai()" | Code gui for MainForm | "MRBS-v5.2" | Continous
|  | 11:00 | 13:22 | 2:22 | Implement Function "loadNgayCuaTuanHienTai()" | Code gui for MainForm | "MRBS-v5.2" | Continous
|  | 17:00 | 19:58 | 2:58 | Implement Function "loadNgayCuaTuanHienTai()" | Code gui for MainForm | "MRBS-v5.2" | Done
| 2012-07-26 | 17:24 | 20:29 | 3:05 | Implement Function "loadNgayCuaTuanHienTai()" | Unit test | "MRBS-v5.2" | Continous
| 2012-07-27 | 12:00 | 16:00 | 4:00 | Implement Function "loadNgayCuaTuanHienTai()" | Rework code gui MainForm | "MRBS-v5.2" | Continous
|  | 17:30 | 19:00 | 1:30 | Implement Function "loadNgayCuaTuanHienTai()" | Rework code gui MainForm | "MRBS-v5.2" | Continous
| 2012-07-28 | 9:53 | 10:35 | 0:42 | Implement Function "loadNgayCuaTuanHienTai()" | Rework code gui MainForm | "MRBS-v5.2" | Continous
| 2012-07-30 | 13:02 | 19:15 | 6:13 | Implement Function "loadNgayCuaTuanHienTai()" | Rework code gui MainForm | "MRBS-v5.2" | Continous
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00

## SAD-Rework
Time Recording Log For: Rework Final Project
Name: | Le Thi Bich Van |  |  | Date: |  | 2012-07-11
HOURS
Week | Date | Start | Stop | Delta Time | Type | Activity | Artifact | Status | U
| 2012-07-11 | 16:53 | 18:30 | 1:37 | Project Management | Define overal Schedule | K15T1-Team1-FinalProject-PlanRework-2010.mpp | Done
| 2012-07-12 | 8:01 | 8:44 | 0:43 | Project Management | Define detail Schedule | K15T1-Team1-FinalProject-PlanRework-2010.mpp | Continus
1 |  | 10:00 | 12:45 | 2:45 | Project Management | Define detail Schedule | K15T1-Team1-FinalProject-PlanRework-2010.mpp | Done
| 2012-07-13 |  |  | 0:00 | Architecture Design | Team Meeting
| 2012-07-14 |  |  | 0:00
| 2012-07-15 |  |  | 0:00
| 2012-07-16 |  |  | 0:00
2 | 2012-07-17 |  |  | 0:00
| 2012-07-18 |  |  | 0:00
| 2012-07-19 |  |  | 0:00
| 2012-07-20 |  |  | 0:00
| 2012-07-21 |  |  | 0:00
3 | 2012-07-22
4
5
6
7
8
9
10
11