## Top Viking's risks
Risk and Description | Type of risk | Probability | Impact | Priority | Recommendation
Task does not obvious | Schedule | Certainly | Very High | 1 | 1.Use WBS to indentify task. 2.Moniter plan.
Estimate plan do not exactly | Schedule | Certainly | Very High | 2 | Training skills make plan.
Lack management change | Plan | Certainly | Very High | 3 | Monitor and control make decisions ontime.
Requirements and customer's need not enough | Develop | Certainly | Very High | 4 | Improve communication with customer.
Estimate budget do not exactly | Budget risk | Possible | Medium | 5 | Estimate budget carfully.
Architect design do not exactly | Develop risk | Possible | High | 6 | Must analysis clearly all requiments and review period design
Estimate human resource not enough | Resource risk | Likely | Low | 12 | You should have resources backup for your project
Developer not skill for develop project and must retraining | Resource risk | Possible | Medium | 11 | Prepare full skills for impliment project
PM not monitor and control progress | Resource risk | Likely | Low | 13 | This is mistake of PM, we need make method prevent
Architect design not exactly | Develop risk | Possible | High | 7 | Must analysis clearly all requiments and review period design
Lack equipment for develop project | Resource risk | Likely | Medium | 9 | You must define resource before implement project
Enviroment effect performance of personel( Ex: conflict between some member) | People risk | Likely | Medium | 14 | Create enviroment communication for team member of project
The scope of the project is not clearly outlined | Scope risk | Possible | High | 8 | Define clearly outlined with customer
Maket exchange when product deliverables | Vision risk | Likely | Medium | 10 | Have vision far about trend future