## Top Viking's risks
ID | Risk and Description | Type of risk | Probability | Impact | Priority | Recommendation
1 | Task does not obvious | Schedule | Certainly | Very High | 1 | 1.Use WBS to indentify task. 2.Moniter plan.
2 | Estimate plan do not exactly | Schedule | Certainly | Very High | 2 | Training skills make plan.
3 | Lack management change | Plan | Certainly | Very High | 3 | Monitor and control make decisions ontime.
4 | Requirements and customer's need not enough | Develop | Certainly | Very High | 4 | Improve communication with customer.
5 | Estimate budget do not exactly | Budget | Possible | Medium | 5 | Estimate budget carfully.
6 | Architect design do not exactly | Develop | Possible | High | 6 | Must analysis clearly all requiments and review period design
7 | Architect design do not exactly | Develop | Possible | High | 7 | Analysis all requiments then design.
8 | The scope do not clearly outlined | Scope | Possible | High | 8 | Define clearly outlined with customer.
9 | Lack equipment | Resource | Likely | Medium | 9 | You must define resource before implement project
10 | Maket exchange when product deliverables | Vision | Likely | Medium | 10 | Have vision far about trend future
11 | Developer not skill for develop project and must retraining | Resource | Possible | Medium | 11 | Prepare full skills for impliment project
12 | Estimate human resource not enough | Resource r | Likely | Low | 12 | You should have resources backup for your project.
14 | PM not monitor and control progress | Resource | Likely | Low | 13 | This is mistake of project manager, we need make method prevent.
15 | Enviroment effect performance of personel | People | Likely | Medium | 14 | Create enviroment communication for team member of project.