## Sheet1
No. | Measure | Why we measure | Source | Data Collection | Metric | Description for Metric
1 | Progress | 1. Provide the status of project 2. Measure the percetage of the tasks completed (PoTC) 3. Measure the percentage of the tasks completed on time (PoTCT) | 1. Schedule 2. Project tracking spreadsheet | 1. Tasks on WBS 2. Tasks completed on time (TCoT) 3. Tasks completed (TC) | 1. PoTC = TC/Tasks on WBS 2. PoTCT = TCOT/TC | Project manager can: 1. follow the progress of project to control and manage team members. 2. make a decision, a new plan
2 | Cost
3 | Quality
4 | Defect
5 | Customer satisfaction | 1. That is a strong predictor of customer retention, customer loyalty and product repurchase. 2. Provide the information about a customer need | 1. Customer satisfaction surveys | 1. Attribute expectations. 2. Attribute need. 3. Level of satisfaction. 4. Perception of change. 5. Likelihood to Recommend 6. Repeat Purchase Likelihood | 1. % attribute expectation 2. % attribute need 3. % perception of change 4. % satisfaction | Project manager can: 1. know how customer satisfaction to improve in the next product. Maketing team can: 1. retain existing customers and add new customers.