## Sheet1
No. | Measure | Why we measure | Source | Data Collection | Metric | Description for Metric
1 | Progress | 1. Provide the status of project 2. Đo % công việc hoàn thành 3. Đo % công việc hoàn thành đúng tiến độ | 1. Schedule 2. Project tracking spreadsheet | 1. Tasks on WBS 2. Tasks completed on time (TCOT) 3. Tasks completed (TC) | 1. % công việc hoàn thành = TC/WBS 2. % công việc hoàn thành đúng tiến độ = TCOT/TC | 1. help manager follow the progress of project. Control and monitor activities in develop team. 2. help manager make decision, prepare new plans.
2 | Cost | 1. Project cost performed report. 2. % actual cost performed devide budget. 3. % estimate cost devide budget. 4. % Cost of fixing a defect. | 1. Defect of project. 2.Project tracking spreadsheet | 1. Estimates & Actuals Cost project. 2.Resource Estimates & Actuals cost project. | Cost variance(CV) = BCWP - ACWP | 1. help manager follow the cost of project. Control and monitor activities in develop team project. 2. help manager make decision, have budget anticipate for project.
3 | Quality | 1. Resolve process issues. 2. Resolve training issues. 3. Resolve tool issues. 4. Resolve systemic issues. 5. Resolve people issues. | 1. Project tracking spreadsheet | 1. Project quality attributes Spreadsheet. 2. Customer satisfic | 1. rate % of attributes completed. 2. rate % function satisfic customer. | 1. help for customer know quality product. 2. Help for customer satisfic with right product