## SEP
Time Recording Log For: SEP Project
SUMMARY: TIME FOR DOING PROJECT
Name: | Dang Huy Son |  |  | Date: |  | 2012-05-21
[10 empty] | WORKS/ARTIFACTS | HOURS
Week | Date | Start | Stop | Delta Time | Phase | Activity | Artifact | Status | U | Requirement
1 | 21st May |  |  | 0:00 | Requirement | analyze and propose requirements |  |  |  | Ananlysis & Design
| 25th May |  |  | 0:00 | Requirement | analyze and propose requirements |  |  |  | Development
| 27th May |  |  | 0:00 | Planning + PM | analyze and propose process and WBS | Made WBS without timeline. Prepare process |  |  | Testing
| 28th May |  |  | 0:00 | Planning + PM | doing WBS | WBS without timeline, update WBS
| 1st Jun |  |  | 0:00 | Ananlysis & Design | Analyze and develop SAD base on project of SAD course |  |  |  | Packaging & Deployment
| 8th Jun |  |  | 0:00 | Ananlysis & Design | Design draft of UI Analyze feature of UI | UI ver 0.1 |  |  | Planning + PM
| 9th Jun |  |  | 0:00 | Ananlysis & Design | Design UI | UI ver 0.2 |  |  | CM
| 10th Jun |  |  | 0:00 | Ananlysis & Design | Design UI | UI ver 0.3 - 0.4 |  |  | Report
| 15th Jun |  |  | 0:00 | Ananlysis & Design | Design UI | Ver 0.5 ver 1.0 ver 1.1 |  |  | TOTAL
| 16th Jun |  |  | 0:00 | Requirement | Review requirement |  |  |  | ON AVERAGE (hours/week)
| 19th Jun |  |  | 0:00 | Ananlysis & Design | Design UI | Ver 1.2
| 23rd Jun |  |  | 0:00 | Requirement | Review and analyze requirement for UI | ver 1.2.1
| 26th Jun |  |  | 0:00 | Ananlysis & Design | Design UI | ver 1.3
| 12th Jul |  |  | 0:00 | Ananlysis & Design | Review database table
| 1st Aug |  |  | 0:00 | Ananlysis & Design | Design email class | Email class Email control class
| 2nd Aug |  |  |  | Development | Email
| 3rd Aug |  |  | 0:00 | Development | Email | Final version
| 6th Aug |  |  | 0:00 | Development | Email | Update email class
| 7th Aug |  |  | 0:00 | Ananlysis & Design | Update SAD | Update SAD and release ver 1.0
| 9th Aug |  |  | 0:00 | Development Ananlysis & Design | Email Show booking status | Integrate email with program Show booking status in calendar Release ver 1.1 SAD
| 11th Aug |  |  | 0:00 | Ananlysis & Design | Update SAD | Release ver 1.2 SAD
| 12th Aug |  |  | 0:00 | Ananlysis & Design | Update SAD | Release ver 1.3 SAD
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
7 |  |  |  | 0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00

## SAD-Rework
Time Recording Log For: Others Project
SUMMARY: TIME FOR DOING PROJECT
Name: | Dang Huy Son |  |  | Date: |  | 2012-05-30
[10 empty] | WORKS/ARTIFACTS | HOURS
Week | Date | Start | Stop | Delta Time | Type | Activity | Artifact | C | U
1
TOTAL
ON AVERAGE (hours/week)
2
3
4
5
6
7
8
9
10
11