## Milestone status
Milestone | Plan | Actual
Inception | 01-Thg6 | 02-Thg6
Elaboration | 20-Thg6 | 25-Thg6
Construction | 10-Thg7 | 15-Thg8
Transition | 15-Thg1
Close-out | 20-Thg2
ai ve dum minh voi, minh ko bik ve cai nay

## Defect status
Iteration | Opened | Fixed | Closed | ReOpend
| 48% | 30% | 20% | 2%
Iteration | Opened | Fixed | Closed | ReOpend
1 | 30 | 15 | 0 | 0
2 | 60 | 30 | 20 | 2
3 | 75 | 55 | 50 | 5

## Analysis Budget
Salary | 1152800 | 62%
Benefits | 22040 | 1%
Staff Expenses | 115280 | 6%
Capital Expense | 46112 | 3%
Change Management | 267246.4 | 14%
Risk Management | 267246.4 | 14%
1870724.8

## Headcount
| Year 1 | Year 2 | Year 3 | Year 4
Project manager | 12 | 12 | 12 | 12
System architect | 3 | 1 | 1 | 1
System analyst | 2 | 1 | 1 | 1
Developer | 36 | 2 | 2 | 2
Tester | 18 | 1 | 1 | 1
Technical writer | 2 | 0 | 0 | 0
Functional management | 12 | 0 | 0 | 0