## Top Viking's risks
ID | Risk and Description | Type of risk | Probability | Priority
1 | Customer don’t know what their needs ,set out thinks is ambigous | Requirement risk | Likely | Medium
2 | Estimate plan don't exactly | Schedule risk | Certainly | Very High
3 | Lack management risks and change | Plan risk | Certainly | Very High
4 | Estimate budget not enough | Budget risk | Possible | Medium
5 | Estimate human resource not enough | Resource risk | Likely | Low
6 | Collect not enough requirements and don't meet customer when need | Develop risk | Certainly | Very High
7 | Task does not define clearly, lack of necessary work task, unreasonable allocation in each period | Schedule risk | Certainly | Very High
8 | Developer not skill for develop and time training | Resource risk | Possible | Medium
9 | PM not monitor and control progress | Resource risk | Likely | Low
10 | Architect design not exactly | Develop risk | Possible | Medium
11 | Lack equipment for develop project | Resource risk | Likely | Medium